## Cover Sheet
On-going Progress Update and Disbursement Request and LFA On-going Progress Review and Disbursement Recommendation
In completing this report, please refer to the detailed "Guidelines for completing the PR “ongoing progress update and disbursement request”, and LFA “ongoing progress review and disbursement recommendation”
During the lifetime of a grant, the Global Fund periodically disburses funds to the Principal Recipient (PR) based on demonstrated program performance and financial needs for the following period of implementation. The PR’s ongoing progress update and disbursement request (PU/DR) is both a progress report on the latest completed period of program implementation and a request for funds for the following period of implementation. Its purpose is to provide an update of the programmatic and financial progress of a Global Fund-financed grant, as well as an update on fulfillment of conditions precedent, management actions and other requirements. The PU/DR, alongside the Local Fund Agent (LFA) ongoing progress review and disbursement recommendation (short-form: LFA-verified PU/DR), forms the basis for the Global Fund’s disbursement decision by linking historical and expected program performance with the level of financing to be provided to the PR. One Excel file contains both the PR’s PU/DR and the LFA-verified PU/DR. The PR should only complete the worksheets of the file pertaining to the PU/DR (the worksheet tabs color-coded in green), whereas the LFA should complete the worksheets of the file pertaining to the LFA-verified PU/DR (the worksheet tabs color-coded in blue). The Excel file also includes a reference checklist of supporting documents for the PU/DR review (the worksheet tab color-coded in yellow). This checklist is included for information and not for completion. The PU/DR should be completed by the PR of a Global Fund grant for every period in which a progress update is required, usually either on a quarterly, semiannual or annual basis, regardless of whether or not a disbursement is being requested. Once a year, the PR is expected to submit the Enhanced Financial Report (EFR) as part of the PU/DR (there is a dedicated tab for EFR in the Excel file). The PR is required to submit the PU/DR to the LFA within 45 calendar days from the closing date of the relevant progress update period when the report does not contain the EFR (as indicated in the performance framework of Annex A of the grant agreement) and within 60 calendar days when the report contains the EFR (once a year). The LFA should complete and submit a signed copy of the LFA-verified PU/DR to the Global Fund within ten working days after receiving the final signed version of the PU/DR from the PR and within 13 working days when the PU/DR report contains the EFR (once a year), unless agreed otherwise with the FPM (The LFA does not need to submit original/hard copies of each PU/DR reports. However, these documents should be available at the LFA’s offices for any audit/reviews. Also, the LFA should be ready at all times to submit these originals to the Secretariat upon request). In this report the LFA should provide an analysis and comments based on verification of the PR-reported information, document grant risks and recommendations for improving program implementation, and finally, provide a performance rating to the grant and disbursement recommendation for the Global Fund’s consideration. In defining the performance rating and recommending a disbursement amount, the LFA should use the Grant Rating Methodology of the Global Fund (as described in Annex 2 and communicated at various regional meetings and LFA training events) along with the Excel version of the Grant Rating Tool (to be provided to LFAs) to support the calculation of Indicator Rating.
Upon completion, this form should be submitted (with supporting documentation) to the Local Fund Agent and copied to the Global Fund.

## PR_Programmatic Progress_1A
On-going Progress Update and Disbursement Request | [13 empty] | Select
AIS (AIDS Indicator Survey)
BSS (Behavioral and Surveillance Survey)
GENERAL GRANT INFORMATION | [13 empty] | Census
Country: |  | Union of Myanmar | [11 empty] | Clinical cohort follow-up studies
Disease: |  | Malaria | [11 empty] | DHS/DHS+ (Demographic and Health Survey)
Grant Number: |  | MYN-S10-G07-M | [11 empty] | MICS (Multiple Indicator Cluster Survey)
Principal Recipient: |  | UNOPS | [11 empty] | MIS (Malaria Indicator Survey)
Program Start Date: |  | 2011-01-01 | [11 empty] | WHO Global report/estimates
Currency: |  | USD | [11 empty] | Other (type as appropriate)
PROGRESS UPDATE
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 1
Progress Update - Period Covered: |  | Beginning Date: | 2011-01-01 | End Date: | 2011-03-31
Progress Update - Number: |  | 1
DISBURSEMENT REQUEST
Disbursement Request - Disbursement Period: |  | Cycle: | Quarter | Number: | 2
Disbursement Request - Period Covered: |  | Beginning Date: | 2011-04-01 | End Date: | 2011-06-30
Disbursement Request - Number: |  | 2
Section 1: Programmatic Progress
Note: The table below should contain those Impact/Outcome indicators that are (1) due for reporting during the current year of a grant and (2) those reporting on which is overdue from the previous periods.
A. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  |  | Baseline (if applicable) |  | Year of Target | Intended Target | Report Due Date | Actual Result | Data Source of Results | Comments on results on Impact/Outcome indicators and data sources, and any other comments
[6 empty] | Value | Year
Outcome | Percentage of households with at least one LLIIN/ITN |  |  |  |  | 5.65% | 2008 | 2011 | 53% | 31-12-2011 | - | Household survey | Indicator will be captured through health facility assessment and community based surveys planned in P2 of Year 1.
Outcome | Percentage of population at risk sleeping under an LLIN/ITN the previous night |  |  |  |  | Not available | Jun-2010 | 2011 | To be determined (TBD) | 31-12-2011 | - | Household survey | Indicator will be captured through health facility assessment and community based surveys planned in P2 of Year 1.
Outcome | Proportion of confirmed malaria cases treated in accordance with national malaria treatment guidelines within 24 hrs of onset of symptoms |  |  |  |  | 25% | 2008 | 2011 | 30% | 31-12-2011 | - | VBDC | Indicator will be captured through health facility assessment and community based surveys planned in P2 of Year 1.

## PR_Programmatic Progress_1B
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: |  |  | MYN-S10-G07-M
Progress Update - Reporting Period: |  |  | Cycle: | Quarter | Number: | 1
Progress Update - Period Covered: |  |  | Beginning Date: | 2011-01-01 | End Date: | 2011-03-31
Progress Update - Number: |  |  | 1
Note: All programmatic indicators contained in the current Performance Framework should be listed, regardless of whether there are targets/results for the period covered by the Progress Update or whether the targets have been met in previous periods.
B. Programmatic Indicators
Objective No. | * Indicator No. | Indicator Description |  |  |  | Tied To | Targets cumulative? | Top 10 indicator? | Baseline (if applicable) |  | Intended Target to date | Actual Result to date | % achievement (Please calculate as appropriate) | Reasons for programmatic deviation from intended target and deviations from the related workplan activities
[9 empty] | Value | Year
1 | 1.1 | Number of LLINs distributed free of charge for people at risk |  |  |  | Current grant | Y-cumulative annually | Yes - Top 10 | 282846 | 2008 |  |  |  | Not due for reporting
1 | 1.3 | Number of mosquito nets treated with insecticide |  |  |  | Current grant | Y-cumulative annually | Yes - Top 10 | 852762 | 2008 |  |  |  | Not due for reporting
2 | 2.1 | Number of blood slides taken and examined |  |  |  | GF and other donors | Y-cumulative annually | No | 499269 | 2008 |  |  |  | Not due for reporting. However, National Malaria Control Programme (NMCP),whose targets are tied to the current grant , took and examined 30,613 blood slides using other resources during the reporting period.
2 | 2.2 | Number of rapid diagnostic testes done and read |  |  |  | GF and other donors | Y-cumulative annually | No | 543941 | 2008 | 40450 | 23106 | 57.12% | Current performance attributed to MCC and MMA. The reported results does not include 112,693 RDTs tests done and read, using 3-DF resources, by the National Malaria Control Programme (NMCP), as it is tied to the current grant.
2 | 2.3 | Percentage of assessed malaria microscopists who met minimum national competency level |  |  |  | Current grant | N-not cumulative | No | Not available | Sep-2010 |  |  |  | Not due for reporting. A series of planned assessment of Malaria microscopists who met minimum national competency level starting P2 to establish baseline and set targets starting from P5.
2 | 2.4 | Number of people with confirmed malaria treated with recommended ACT (disaggrated by age group and sex) |  |  |  | GF and other donors | Y-cumulative annually | Yes - Top 10 | 394529 | 2008 | 10750 | 7039 | 65.48% | Current performance attributed to MCC and MMA. The reported results does not include 43,667 patients treated with ACT by National Malaria Control Programme (NMCP) using 3DF resources, as their results are tied to Current grant.
2 | 2.5 | Number of people with malaria (probable and confirmed) treated with chloroquine (disaggrated by age group and sex) |  |  |  | GF and other donors | Y-cumulative annually | Yes - Top 10 | 239751 | 2008 | 9000 | 8961 | 99.57% | Current performance attributed to MCC and MMA. The National Malaria Control Programme (NMCP), whose targets are tied to the current grant, provided treatment with chloroquine for 35,304 people with malaria (probable and confirmed) using 3-DF funding during the reporting period .
2 | 2.6 | Percentage of health facilities with no reported stock outs of nationally recommended antimalarial drugs lasting more than 1 week at any time during the past 3 months |  |  |  | GF and other donors | N-not cumulative | No | Not available | Jun-2010 |  |  |  | Although it is not due for reporting, the result from MMA which is tied to GF and other donors, for this quarter, is 100%, for all their 235 Quality General Practioners.
2 | 2.7 | Percentage of health care providers who provide antimalarial treatment according to national malaria treatment guidelines among those surveyed (disaggrated by categories of providers) |  |  |  | GF and other donors | N-not cumulative | No | Not available | Jun-2010 |  |  |  | Not due for reporting. The Health Facility Survey is planned for P2, using GF resources and supplemented with data from supportive supervision and monitoring visits.
4 | 4.1 | Number of village health volunteers trained and supported for malaria prevention and control |  |  |  | GF and other donors | Y-cumulative annually | Yes - Top 10 | 136 | 2008 | 224 | 0 | 0% | No trainings were conducted due to delays in approving Training Plans. However, training plans were approved on 18th April, 2011 SR has made adjustments to catch-up with the lost time for trainings.
5 | 5.1 | Number of health staff trained and retrained |  |  |  | GF and other donors | Y-cumulative annually | Yes - Top 10 | 8147 | 2008 | 129 | 45 | 34.88% | MMA conducted trainings using 3-DF funding, as tragtes were untied. However, MCC,VBDC and MRCS did not conduct any trainings due to delays in approving Training Plans. However, training plans were approved on 18th April, 2011.SR has made adjustments to catch-up with the lost time for trainings .
[6 empty] | Select | Select | Select |  |  | - | - | #VALUE!
[6 empty] | Select | Select | Select |  |  | - | - | #VALUE!
[6 empty] | Select | Select | Select |  |  | - | - | #VALUE!
[6 empty] | Select | Select | Select |  |  | - | - | #VALUE!
[6 empty] | Select | Select | Select |  |  | - | - | #VALUE!
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
[6 empty] | Select | Select | Select |  |  | - | -
* Indicator No. should correspond to the indicator number listed in the approved Performance Framework of the grant (1.1, 1.2, etc.)
C. Analysis of data quality and reporting issues (!) This section should contain (1) a summary of issues related to data quality and reporting on programmatic indicators, and any relevant issues which are not covered in 'Reasons for programmatic deviation', and (2) remedial actions that are underway or planned to address these issues.
An average completion rate of 96% was observed with reports submitted by SRs. A closer analysis showed that 5 out of 5 (100%) SRs submitted accurate reports, 4 (80%) out of 5 SRs included indicators due for reporting, 5 out of 5 (100%) SRs provided programmatic rationale for each indicator performance. Two (2) out of 5 Malaria SRs (40%) submitted reports within the specified timelines.All sub-recipients (100%) had concerns and lack of clarity related to the concept of tied/untied indicators.With implementation expected to gain momentum in Q2, the PR will provide a more in-depth qualitative and quantitative analysis of these challenges in the next reporting period.On-site data validation at SR offices and further clarifications is a good practice not only for ensuring good quality data but also for better understanding of GF reporting demands and requirements. In this quarter PR identified relevant supporting documents that the PR will need for data validation at HQ level for reporting.The apparent under-performance and inability to report on some indicator-result in this quarter are due to tied/untied issues in the performance framework and delayed disbursement, which has since been discussed with the GF/LFA. Based on the experience gained during the data validation visits and analyzing SRs feedback to UNOPS, on-site data validation and quarterly coordination meeting with PR and SR will be carried out as per M&E work plan. The PR is calling for a collective M&E workshop in June 2011 with all SRs to further address GF reporting demands and requirements and strengthen SRs M&E capacities. Quarterly work plans are revisited and refined with all SRs to ensure catch-up on deliverables in the remaining quarters of the year.

## PR_Grant Management_2
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | MYN-S10-G07-M
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 1
Progress Update - Period Covered: | Beginning Date: | 2011-01-01 | End Date: | 2011-03-31
Progress Update - Number: | 1
Section 2: Grant Management
A. PR COMMENTS ON THE FULFILLMENT OF CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER THE GRANT AGREEMENT
! Please include in this table the CP number as per Grant Agreement and full text of CPs and/or other special conditions due for fulfillment during this period or outstanding from previous periods. ! Some Special Conditions may apply to more than one period of grant implementation. Their fulfillment during one period does not automatically imply fulfillment in subsequent periods. The LFA should verify that the status of such conditions is reported by the PR during each period concerned.
Conditions Precedent and/or other special conditions |  |  | Status | PR Comments on Progress of Implementation
1. Conditions Precedent to First Disbursement (Terminal Date as stated in block 7A of the Face Sheet) (a) the delivery by the Principal Recipient to the Global Fund of the Principal Recipient’s operating procedures for managing the flow of Grant funds from the time of Global Fund disbursement through to the funds arriving in the Myanmar Country Office of the Principal Recipient, including the operating procedures for the exchange and management of Grant funds in local currency. |  |  | Met | The GF has approved the PRs Financial Management Policies and Procedures Manual (FPPM) on the 2nd of May,which describes the procedures for managing the flow of Grant funds from the time of Global Fund disbursement through to the funds arriving in the Myanmar Country Office of the Principal Recipient, including the operating procedures for the exchange and management of Grant
1.(b) the delivery by the Principal Recipient to the Global Fund of an Internal Audit Plan, in form and substance satisfactory to the Global Fund, outlining the audit coverage at both Principal Recipient and Sub-recipient levels. |  |  | Unmet - In Progress | The PR has submitted the 2nd iteration of the Internal Audit Plan (Compliance Manual and Verification Plan), outlining the internal verification coverage at both Principal Recipient and Sub-recipient levels, on 13 May 2011 following GF feedback on the 1st submission on 1 April. UNOPS is currently waiting for the Global Fund review and approval.
2. Conditions Precedent to Disbursement to Sub-recipients (a) the delivery by the Principal Recipient to the Global Fund of the Principal Recipient’s operating procedures for disbursements of Grant funds to the Sub-recipients. |  |  | Met | The GF has approved the PRs Financial Management Policies and Procedures Manual (FPPM) on the 2nd of May,which describes the procedures for managing the flow of Grant funds from the time of Global Fund disbursement through to the funds arriving in the Myanmar Country Office of the Principal Recipient, including the operating procedures for the exchange and management of Grant.
2. (b) the delivery by the Principal Recipient to the Global Fund of a plan, in form and substance satisfactory to the Global Fund, for the oversight of Sub-recipients. |  |  | Met | The PR's Financial Management Policies and Procedures Manual (FPPM) and PR programme Management Procedures Manual were submitted on 15 March 2011. The GFATM approved both on 2 May and 7 April 2011 respectively.
2 . (c) the delivery by the Principal Recipient to the Global Fund of evidence, in form and substance satisfactory to the Global Fund, that the Principal Recipient has assessed the capacity of each Sub-recipient and confirmed that each Sub-recipient either meets the minimum Global Fund requirements in relation to financial management or has developed a capacity building plan to address any significant weaknesses identified. |  |  | Met | PR presented to the Global Fund a status update on capacity building of SRs in the area of finalcial management in March 2011. LFA assessment of the SR capacities in January of 2011 resultes in 3 LNGOs eligible to receive advance funds. LFA conducted further assessments of the remaining 3 SRs zero cash flow in March 2011, and the GF has approved on 13 April 2011 that all LNGOs can receive advance funds. PR conducted SR capacity building workshops with all LNGOSs in April 2011. A dedicated unit is continuously working with SRs to improve capacities in the area of financial management.
2. (d) the delivery by the Principal Recipient to the Global Fund of a plan, in form and substance satisfactory to the Global Fund, for the audit of the expenditures of Sub Recipients under the Program. |  |  | Met | The FPPM addressed the SR audit in detail - approved by GFATM on 2 May 2011. Workplans for the upcoming SR annual audits are going to be developed by the contracted audit firm for annual SR audits, based on the TOR designed by the PR. Such work towards finalisation of the TOR for the annual SR audits and the selection of the audit firm conducting the audits is ongoing and will be completed towards the beginning of the second half of the year.
3. Conditions Precedent to Disbursement for Procurement of Health Products (as defined in Article 18 of the Standard Terms and Conditions) (a) the delivery by the Principal Recipient to the Global Fund of a plan for the procurement, use and supply management of Health Products for the Program as described in subsection (b) of Article 18 of the Standard Terms and Conditions of this Agreement (the “PSM Plan”); |  |  | Met | PSM Plans have been approved Oct 2010. Procurement is ongoing carried out by UNOPS India Office as Procurement Agent. HIV PSM Plan has been revised and approved by GFATM on 2 February 2011.
3. (b) the written approval by the Global Fund of the PSM Plan. |  |  | Met | PSM Plans have been approved Oct 2010. Procurement is ongoing carried out by UNOPS India Office as Procurement Agent. HIV Plan has been revised and approved by GFATM on 2 February 2011.
3. (c) the delivery by the Principal Recipient to the Global Fund, of evidence, in form and substance satisfactory to the Global Fund, that the Principal Recipient has recruited qualified staff members to manage the Procurement and Supply Management of Health Products for the Program. |  |  | Met | Recruitment has been completed and all forseen posts are adequately filled. However, One post, the Intl Procurement Officer, will be filled only following a successful review of UNOPS to conduct procurement in the UNOPS PR office in Myanmar – planned from 1 July 2011. Intensive trainings are being carried out of all S/M to prepare for LFA assessment.
4. Conditions Precedent to Disbursement or Use of Grant funds for upgrading of the storage and distribution system of the Health Products (Terminal Date as stated in block 7B of the Face Sheet) (a) the delivery by the Principal Recipient to the Global Fund, in form and substance satisfactory to the Global Fund, of an assessment report of the storage and distribution system of the Health Products. |  |  | Met | The assessment report of the storage and distribution system of health products submitted and Renovation Plan submitted to GF on 14 February 2011– GF partially approved on 18 March 2011: central warehouses can be renovated, S/D level storages need further clarification to be provided to GF.
4. (b) the delivery by the Principal Recipient to the Global Fund, in form and substance satisfactory to the Global Fund, of a costed work plan for such upgrading, which shall include timeframes and deliverables for priority improvements. |  |  | Met | The assessment report of the storage and distribution system of health products submitted and Renovation Plan submitted to GF on 14 February 2011 – GF partially approved on 18 March 2011: central warehouses can be renovated, S/D level storages need further clarification to be provided to GF.
C. SPECIAL TERMS AND CONDITIONS FOR THIS AGREEMENT 1. The parties to this Agreement acknowledge that as of the date of this Agreement, the Global Fund has received the commitment of the Host Government to the following: (a) to issue renewable annual multi-entry visas for the Principal Recipient and the Local Fund Agent personnel in advance of their start dates of employment as notified by either the Principal Recipient or the Local Fund Agent, and (b) to allow the Principal Recipient, the Local Fund Agent, and the Global Fund representatives ad-hoc access to project implementation sites. |  |  | Met | MOU with MoH was signed 18 November 2010.
2. The Parties to this Agreement acknowledge and agree that expenditure of Grant funds or implementation of the Program activities shall not take place in locations where staff members or individuals contracted and acting on behalf of the Principal Recipient, Sub recipients, the Local Fund Agent or the Global Fund are denied access. The Principal Recipient acknowledges and agrees that in the event that the Principal Recipient, Sub-recipients, Local Fund Agent or the Global Fund are denied access to project sites, the Global Fund may discontinue the funding for activities occurring in such project site or resort to remedies of suspension and termination under this Agreement. |  |  | Met | PR complies and list of townships in which the GF funded activities are being implemented, is attached, as per supporting document. NB: NAP and NMCP are revisitng their coverage due to other doner initiatives supporting activities and to avoid overlapping. A revised Tsp list will be developed and sent to GFATM for apoproval in June 2011.
3. In the event that an additional Sub-recipient is selected during the Commitment Period, the Parties to this Agreement acknowledge and agree that prior to the disbursement of Grant funds by the Principal Recipient to such Sub-recipient, the Principal Recipient shall furnish to the Global Fund, in form and substance satisfactory to the Global Fund, the following: i. evidence demonstrating that the Principal Recipient has conducted a comprehensive assessment of the Sub-recipient; |  |  | Met | UNOPS will follow such procedures, as outlined in the Financial Management Policies and Procedures Manual (FPPM) and the Programme Management Procedures Manual (PMPM).
3.(ii). evidence demonstrating that the Principal Recipient has signed an agreement with the Sub-recipient, which, without limitation, shall include a budget, workplan, implementation and financial and programmatic reporting responsibilities of the Sub-recipient; |  |  | Met | All SR Agreements have been signed with all SRs - SR Agreements have been shared with LFA/GFATM between 3rd February 2011. UNFPA and UNOPS could not agree on the proposed conditions of the SR Agreement and hence UNFPA is no longer an SR. This has been communicated at the 9th CCM meeting on the 3rd of May 2011. Minutes of the meeting already circulated on 6th of May 2011. Discussions with NAP to ensure TA provision in TCP (UNFPA's area of work) are ongoing to allocate the funds that became available as a result of this drop-out.
3.(iii). details identifying the financial institution or institutions into which Grant funds will be disbursed for the benefit of the Sub-recipient. |  |  | Met | Disbursements are ongoing as per GF approval of Financial Management Policies and Procedures Manual (FPPM). Details of Bank accounts are provided as supporting document to this PU/DR.
3.(iv). documentation demonstrating that the Sub-recipient has received training on monitoring and evaluation responsibilities sufficient to meet its requirements under the Program. |  |  | Met | Trainings to build adequate M&E capacities in SRs took place between 21 January and 25 March 2011. Documentation is provided as supporitng documentation.
4. Notwithstanding Section C.3 above, the Global Fund reserves the right to request the assessment by the Local Fund Agent of any additional Sub-recipient selected in accordance with this Agreement. |  |  | Met | No action necessary from the PR
5. The Principal Recipient and the Global Fund agree that, without the prior written approval of the Global Fund, the Principal Recipient shall not advance Grant funds to any implementing entity, except for the United Nations entities and the International Union against Tuberculosis and Lung Disease. With exception of the funding provided by the Principal Recipient to United Nations entities and the International Union against Tuberculosis and Lung Disease, the Principal Recipient shall provide funding to implementing entities only on a reimbursable basis by adhering to a zero cash balance policy, which limits funding to either a) reimbursing actual expenditures made in accordance with budgets and work plans which have been verified by the Principal Recipient or b) by the Principal Recipient making direct payments to vendors for goods and services procured to support the activities of such implementing entities. |  |  | Met | PR Complies.
6. The advance of Grant funds to implementing entities for activities at the township level is subject to the satisfaction of each of the following conditions: ( a) the delivery by the Principal Recipient to the Global Fund of a plan, in form and substance satisfactory to the Global Fund, for the management of the fund flow process at the township level (the “Fund Flow Mechanism ”); |  |  | Met | The GF has approved the PRs Financial Management Policies and Procedures Manual (FPPM) on the 2nd of May, which describes the procedures for managing the flow of Grant funds from the time of Global Fund disbursement through to the funds arriving in the Myanmar Country Office of the Principal Recipient, including the operating procedures for the exchange and management of Grant and established Funds Flow Mechanism to comply with zero cash flow policy.
6.(b) the written approval by the Global Fund of the Fund Flow Mechanism. |  |  | Met | The GF has approved the PRs Financial Management Policies and Procedures Manual ( FPPM) on the 2nd of May, which describes the procedures for managing the flow of Grant funds from the time of Global Fund disbursement through to the funds arriving in the Myanmar Country Office of the Principal Recipient, including the operating procedures for the exchange and management of Grant and established Funds Flow Mechanism to comply with zero cash flow policy.
7. The Global Fund reserves the right to unilaterally revoke the operation of the Fund Flow Mechanism and request the Principal Recipient to submit to the Global Fund for approval an adjusted Fund Flow Mechanism plan to implement the activities covered under this system using a zero cash balance policy as defined under Section C.5. In this event, the Principal Recipient shall be entitled to submit a request to access the supplementary funds budgeted for the financial management and implementation of the zero cash balance policy related to the activities previously covered under the Fund Flow Mechanism. For the avoidance of doubt, parties acknowledge that supplementary funds are currently budgeted in the amount of US$84,000 and may not be utilized for any other purpose, without written approval of the Global Fund. |  |  | Met | PR complies
8. The Principal Recipient and the Global Fund acknowledge and agree that the financing of activities implemented by the Sub-recipients shall be subject to the foregoing conditions. a (i) health care and service provision. a.(ii) patient support costs, a.(iii) the supply management function, a.(iv) provision of essential equipment, a.(v) monitoring, supervision and coordination of Program activities a.(vi) training a.(vii) technical and management support to enable decentralised levels of civilian administrations to manage and monitor service delivery a.(viii) domestic travel and accommodation costs incurred in the course of implementation of the Program; |  |  | Met | PR complies. All SR agreements are developed to reflect eligibility of expenses and the PR is monitoring strict compliance.
8.(b) Domestic travel and accommodation costs incurred in the course of the implementation of the Program by Sub-recipients other than UN agencies and the International Union against Tuberculosis and Lung Disease shall not exceed the costs authorized by the rules established by the United Nations Development Programme for Myanmar. The Principal Recipient shall endeavor to harmonize the rates and rules with those being applied by the 3 Diseases Fund. |  |  | Met | PR complies. All SR agreements are developed to reflect eligibility of expenses and the PR is monitoring strict compliance.
8.(c) International travel and accommodation expenses incurred in the course of the implementation of the Program shall be subject to Global Fund approval. |  |  | Met | PR complies. All SR agreements are developed to reflect eligibility of expenses and the PR is monitoring strict compliance.
8.(d) Program activities in support of the government agencies at national, divisional/state, district, township health authority or local civilian administrative level or below must be included in the work plans and budgets of United Nations agencies and such actions, including fund disbursement and commodity provision, shall be monitored by the Principal Recipient at least on a quarterly basis; |  |  | Met | PR complies. All SR agreements are developed to reflect eligibility of expenses and the PR is monitoring strict compliance.
8.(e). Support to government-implemented components of the national programs shall not include staff salaries and allowances, recruitment fees, international fellowships, recurrent costs or expenses for rehabilitation of Ministry of Health facilities without prior written approval of the Global Fund; and |  |  | Met | PR complies. All SR agreements are developed to reflect eligibility of expenses and the PR is monitoring strict compliance.
8.(f). Support to patients using public health facilities can be made for supporting the care for patients suffering from HIV, tuberculosis and malaria in the form of provision of in kind drugs, medical supplies and consumables and diagnostic procedures directly related to HIV, TB and malaria care only. |  |  | Met | PR complies. All SR agreements are developed to reflect eligibility of expenses and the PR is monitoring strict compliance.
9. The Principal Recipient acknowledges and agrees that percentage-based overheads or cost recovery fees of Sub-recipients shall not exceed the amounts established in the budget approved by the Global Fund, unless the Global Fund has expressly authorized in writing the payment of higher amounts. Sub-recipients in receipt of such payments, other than United Nations entities, shall submit their organization’s annual Audited Financial Statements upon request of the Global Fund. |  |  | Met | PR complies. All SR agreements are developed to reflect eligibility of expenses and the PR is monitoring strict compliance.
10. The parties to this Agreement acknowledge and agree that cost recovery charges levied by the Principal Recipient under this Agreement shall be made in accordance with rates mutually agreed by the Principal Recipient and the Global Fund |  |  | Met | PR complies.
11. During the term of this Agreement the Principal Recipient shall maintain a minimum level of staffing consisting, without limitation, of the following professionals of experience and qualifications competitive at international level: a Program Coordinator, a Finance Officer, a Monitoring and Evaluation Officer and a Procurement Officer. In the event that consultants are contracted to cover gaps caused by delays in recruitment, such consultants must have equivalent qualifications and experience. |  |  | Met | PR complies. All S/M are recruited and in-country.
12. The Principal Recipient shall ensure that vehicles or other fixed assets procured or leased by the Principal Recipient or any implementing entity, using Grant funds may be made available to the Host Government or national entities only on a loan basis. The Principal Recipient shall use its best efforts to ensure that vehicles and other fixed assets which have been made available to the Host Government or national entities, by the Principal Recipient or any other implementing entity, including Sub-recipients, on a loan basis are used for Program activities only. The Principal Recipient and implementing entities, including Sub-recipients, shall maintain log books for all vehicles and fixed assets. The Principal Recipient and implementing entities shall ensure that the location of such vehicles and/or fixed assets are known at all times and are available for inspection by staff of the Principal Recipient, Sub-recipient, Local Fund Agent and/or the Global Fund. |  |  | Met | PR complies.
13. The Parties to this Agreement acknowledge and agree that the procurement of supplies and equipment using Grant funds, including supplies and equipment to support the activities of implementing entities, shall be conducted exclusively by the Principal Recipient. The procurement of Health Products will be governed by the Standard Terms and Conditions of this Agreement and Section C.14 of this Agreement. |  |  | Met | PR complies. WHO is procuring its office equipment themselves and other SRs may procure with PR's consent for less than USD 2,500, evaluated by PR on a case by case basis (ref. FPPM). The UNION is conducting activites related to cost categories 'Infrastructure and Equipment' themselves.
14. The Principal Recipient acknowledges and agrees that the procurement of Health Products with the use of Grant funds shall be done through a suitably qualified Procurement Agent (as assessed by the Local Fund Agent and approved by the Global Fund in writing) until the Global Fund has agreed in writing, upon relevant assessment by the Local Fund Agent, that such procurement can be properly managed by the Principal Recipient. |  |  | Met | PR complies.
15. In accordance with Articles 18(b)(2), 18(c) and 18(g) of the Standard Terms and Conditions of this Agreement, the parties agree that the procurement of Medicines will strictly follow the list contained in the PSM Plan, which may include Medicines whose registration has been waived by the National Drug Regulatory Authority of the Union of Myanmar. |  |  | Met | PR complies.
16. No later than 30 June 2011, the Principal Recipient shall deliver to the Global Fund evidence, in form and substance satisfactory to the Global Fund, that the Principal Recipient has established a functional system for storage, distribution, recording and reporting and utilization of information to manage the program, recording and reporting on patient and inventory related information (Management Information System), including a system for validating, analyzing and utilizing the reported information in the management of the programs. The Principal Recipient shall also deliver to the Global Fund, Standard Operating Procedures for storage, distribution of health products, and recording and reporting and utilization of information to manage the program. |  |  | Unmet - In Progress | Development of required documentation in progress.LMIS Manual is due on 30 June.
17. The Global Fund reserves the right to conduct periodic reviews of the Procurement and Supply Management function of the Principal Recipient. |  |  | Met | PR complies.
18. The Principal Recipient shall notify the Global Fund in advance of any proposed changes to the implementation arrangements described in this Agreement. Such proposed change in the implementation arrangements shall be subject to the prior written approval of the Global Fund. |  |  | Met | Interpretation of the condition as per the GFATM instructions (as per telecon minutes from 11 November 2010): "UNOPS does not need to request permission from the Global Fund to make changes which do not exceed 5% of the Phase 1 budget of an SDA or Cost Category provided that these changes are clearly necessary for the successful management and implementation of the program and are in accordance with the approved objectives and activities as documented in the original proposal and grant agreements. These changes should be documented and available for review if requested. The 5% flexibility does not apply in the following situations where the Global Fund should be notified in advance prior to the change being made: i. Increases in the grades, numbers or Level of Effort of Expatriate Staff charged to the grant. ii. Increases in the numbers or grades of Local staff employed by UNOPS, WHO, UNFPA and IUATLD from the submitted organogram (UNOPS) and detailed budgets. iii. Increases in the staff numbers or position types of national SRs (with the exception of technical staff identified through approved capacity building plans or PR assessments), or significant increases (20%) in the salaries for individual positions that are budgeted initially at more than $1,000 per month. iv. Increases in the approved budget for International Travel for any individual organization (PR or SR). v. Introduction or Modifications to percentage based overhead rates from the approved budget. vi. Increases in the budgeted unit costs for the reimbursement of patient user fees. vii. Increases in the numbers of vehicles (including Motorbikes) budgeted for procurement or long-term rental (rental of additional vehicles beyond 1 month) from the approved budget. viii. Introduction of new activities or cost types which have not been specified in the detailed budget should also be notified to the Global Fund."
19. The Principal Recipient shall ensure that the Oversight Plan for Sub-recipients (as described in Section B.2.b above) and the Internal Audit Plan (as described in Section B.1.b above) is implemented as scheduled and shall report any findings arising to the Global Fund on a quarterly basis including measures to address issues identified. |  |  | Met | PR complies.
20. The Principal Recipient shall apply a Conflict of Interest corporate Policy signed by all personnel working for the Principal Recipient on the Program. The Global Fund shall review that the Policy is correctly applied and that such Policy complies with the requirements set forth in Article 28 of the Standard Terms and Conditions of this Agreement. |  |  | Met | PR complies.
21. The Principal Recipient agrees that Grant funds cannot be used to finance WHO positions for the calendar year 2012 unless such support has been approved by the Global Fund by 30 June 2011. |  |  | Met | PR complies.
22. The Principal Recipient shall use its best efforts to co-ordinate the development of a national monitoring and evaluation plan for HIV (the “National M&E Plan”) and to submit a copy to the Global Fund. Prior to submission of the National M&E Plan to the Global Fund, the Principal Recipient shall, upon request, provide progress updates to the Global Fund. |  |  | Met | A National M&E Plan (Malaria) is under development and expected to be finalized in December 2011.
23. The Principal Recipient shall ensure that the United Nations operational rate of exchange applies to currency conversions from United States Dollars into Myanmar Kyats during the term of this Agreement in accordance with the procedures referred to in Section B.1.a above. Notwithstanding above, the parties acknowledge and agree that the International Union against Tuberculosis and Lung Disease is entitled to employ other competitive currency conversion rates, provided that best efforts are used to employ the most beneficial rate available in accordance with their own approved procedures. |  |  | Met | PR complies
24. For the purposes of this Agreement, implementing entities shall include the Principal Recipient, Sub-recipients, Sub-sub-recipients and any other entity or individual that receives Grant funds for implementation of Program activities. |  |  | Met | PR complies
25. Notwithstanding what provided for in Article 3(c) of the Standard Terms and Conditions of this Agreement, any interest or other earnings generated by any Sub-Recipient which is an organization of the United Nations system shall be treated in accordance with the financial rules and regulations of such Sub-recipient. |  |  | Met | PR complies
26. The Global Fund and the Principal Recipient agree that the detailed program evaluations mentioned in Article 15 of the Standard Terms and Conditions of this Agreement are limited to those evaluations previously agreed in the detailed Monitoring and Evaluation Plan. |  |  | Met | PR complies
B. PR REVIEW OF PROGRESS ON IMPLEMENTATION OF OUTSTANDING MANAGEMENT ACTIONS FROM PREVIOUS DISBURSEMENTS
! Please list all issues raised in the last Management Letter from the Global Fund or outstanding from previous Management Letters, and comment on the progress. Please include the date of the management letter and the item number.
Global Fund Management Actions |  | PR Comments on Progress of Implementation
1. Reporting on Conditions: In this disbursement request [DR1] UNOPS did not provide comments on all CPs. In the future all conditions (Special Conditions and Conditions Precedent) should be reported in the PU/DRs, including on-going conditions and those that will be relevant in a future period. (ref:mangement actions requested from GF in a management letter dated 14 December 2010) |  | The PR acknowledges the observation and commits to providing progress updates on all conditions in subsequent DRs.
2. Special Condition 1 requiring long-term visas for the PRs and LFA staff has not been fulfilled as there are still two LFA staff that have not been granted long-term visas. UNOPS should urgently follow up with the MoH to ensure that remaining LFA staff obtain the appropriate long-term visas, as well as the UNOPS staff that do not yet have the necessary documents to relocate to Myanmar. (ref:mangement actions requested from GF in a management letter dated 14 December 2010) |  | SC1 is an acknowledgement of the commitment of the Host Government. Such commitment is demonstrated by the valid MOU between MOH and UNOPS. UNOPS is not in the position to secure visas since issuance of visas is at the sole discretion of MOH and GoUM. UNOPS regularly follows up on visa matters with IHD of MOH. All UNOPS PR staff members have received the requested visas.
3. The PR should submit an expenditure report for the pre-financing period in January 2011 for the LFA to carry out the verification before next disbursement request (ref:mangement actions requested from GF in a management letter dated 14 December 2010) |  | The PR submitted the expenditure report on 10 April 2011. A copy of the expenditure report is provided as part of the supporting documents to this PUDR.
4. Procurement will be conducted as planned by UNOPS IPO with additional levels of review conducted by the Global Fund during this process. Given that IPO is conducting procurement on behalf of both PRs, we kindly ask that UNOPS provide the CCM and Save the Children with regular updates on the status of the procurement and any issues that may emerge that could affect the procurement. (ref:mangement actions requested from GF in a management letter dated 14 December 2010) |  | The PR has provided regular updates to the CCM and STC (weekly) on procurement and other procurement related issues.
5. As UNOPS is aware, we have asked the LFA to verify the various stages of the IPO procurement to be conducted shortly. The Global Fund shared these ToRs with UNOPS on 6 December 2010 and we have received the product list. (ref:mangement actions requested from GF in a management letter dated 14 December 2010) |  | The LFA has since verified the various stages of the IPO procurement for LLINs, Male Condoms, ACTs, ARVs, TB first line drugs and RDTs. For other items it was agreed the GF will have a post award review.
6. Training plan: As per our discussion and the informational note that was sent on Friday December 10, the Global Fund is attempting to address some of the concerns of our Board and the Office of the Inspector General with respect to accountability of expenditures for training activities. (ref:mangement actions requested from GF in a management letter dated 14 December 2010) |  | The GF reviewed and approved the training plans on 18 April 2001 with the exception of NTP Patient Empowerment Workshops, the first quarterly review and evaluation meeting and refresher trainings. Further clarifications were provided to the GF/LFA and the GF approved the NTP Empowerment workshops and Refresher Trainings on 26 April 2011. The PR has since provided a more detailed justification and programmatic rationale for the necessirty of the first quarterly review and evaluation meeting on 5 May 2011 which is currently under review by the GF/LFA.
C. PR COMMENTS ON ANNUAL GRANT REPORTING REQUIREMENTS
! Please indicate a date for the report due for submission. If a report is overdue, indicate the original due date and explain the reason for delay.
Required Documentation |  | Due date (dd-mmm-yy) | Status | Comments
PR Audit Report |  | 2012-06-30 | Preparation on track | PR Audit report submitted to the Global Fund covers SRs.
Enhanced Financial Reporting (EFR) |  | 2012-02-15 | Preparation on track

## PR_Total PR Cash Outflow_3A
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: |  | MYN-S10-G07-M
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 1
Progress Update - Period Covered: |  | Beginning Date: | 2011-01-01 | End Date: | 2011-03-31
Progress Update - Number: |  | 1
Currency: |  | USD
Section 3A: Total PR Cash Outflow
! For RCC grants the cumulative section of the table below should contain cumulative amount from the start of the RCC and not from the start of Phase 1 of the program.
| Budget for Reporting Period | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance |  | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
1. Total PR cash outflow vs. budget | 7276967.52 | 185234.85 | 7091732.67 |  |  | 7276967.52 | 185234.85 | 7091732.67
1a. PR's total expenditures | 1637375.47 | 185234.85 | 1452140.62 | The variance is mainly contributed by lower than expected expenditures in HR and infrastructure and other equipment cost. There was a late recruitment in PR staff especially Field Finance Assistants (due to long process of coordination and getting approval from MoH for FFA stations) and expatriates (due to time-consuming process for visa issuance and due to decline of job offer by some selected candidates) . However, the POs related to Procurement under Infrastructure and Other Equipment, have been issued and outstanding payments are to be made in the second Quarter subject to completion of arrival of supplies. |  | 1637375.47 | 185234.85 | 1452140.62 | The variance is mainly contributed by lower than expected expenditures in HR and infrastructure and other equipment cost. There was a late recruitment in PR staff especially Field Finance Assistants (due to long process of coordination and getting approval from MoH for FFA stations) and expatriates (due to time-consuming process for visa issuance and due to decline of job offer by some selected candidates) . However, the POs related to Procurement under Infrastructure and Other Equipment, have been issued and outstanding payments are to be made in the second Quarter subject to completion of arrival of supplies.
1b. Disbursements to sub-recipients | 5639592.05 | 0 | 5639592.05 | Disbursement could not be done because of delayed approval of CPs by the GF. However, CP2c was approved on 13th of April and CP2a & CP2b &CP2d on 2nd May 2011. |  | 5639592.05 | 0 | 5639592.05 | Disbursement could not be done because of delayed approval of CPs by the GF. However, CP2c was approved on 13th of April and CP2a & CP2b &CP2d on 2nd May 2011.
| Budget for Reporting Period* | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance |  | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
2. Total pharmaceutical & health product expenditures vs. budget | 4057423 | 0 | 4057423 |  |  | 4057423 | 0 | 4057423
2a. Medicines and pharmaceutical products | 681439 | 0 | 681439 | No supplies received yet. No payment made. |  | 681439 | 0 | 681439 | No supplies received yet. No payment made.
2b. Health products and health equipment | 3375984 | 0 | 3375984 | No supplies received yet. No payment made. |  | 3375984 | 0 | 3375984 | No supplies received yet. No payment made.

## EFR Malaria Financial Data_3B
SECTION 3B: MALARIA FINANCIAL REPORTING FORM
Country |  | Union of Myanmar |  |  | PLEASE REFER TO THE "GUIDANCE FOR COMPLETION OF THE ENHANCED FINANCIAL REPORTING TEMPLATE" DOCUMENT TO ASSIST YOU IN COMPLETING THE TEMPLATE
Grant No. |  | MYN-S10-G07-M
PR |  | UNOPS |  |  | TO BE COMPLETED ONLY ONCE A YEAR EXCEPT AT MONTH 18 FOR PURPOSES OF PHASE 2 REVIEW
Currency |  | USD
[6 empty] | dd-mm-yyyy |  |  |  | dd-mm-yyyy
|  |  |  | Current Reporting Period | Start Date: | 2011-01-01 |  | Cumulative Reporting Period | Start Date: | 2011-01-01
[5 empty] | End Date: | 2011-03-31 |  |  | End Date: | 2011-03-31
The end date for the current reporting period and cumulative reporting period must be the same
The "TOTAL" rows in Table A, B and C will have a RED background if the amounts in each table do not agree. If the Totals for each Table agrees, these rows will have a YELLOW background.
A- BREAKDOWN* BY EXPENDITURE CATEGORY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period |  |  |  | All amounts are in: | Budget for Reporting Period | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
# | Category |  |  | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance | 1. Total PR cash outflow vs. budget | 7276967.52 | 185234.85 | 7091732.67 |  | 7276967.52 | 185234.85 | 7091732.67
1 | Human Resources | [10 empty] | 1a. PR's total expenditures | 1637375.47 | 185234.85 | 1452140.62 |  | 1637375.47 | 185234.85 | 1452140.62
2 | Technical Assistance | [10 empty] | 1b. Disbursements to sub-recipients | 5639592.05 | 0 | 5639592.05 |  | 5639592.05 | 0 | 5639592.05
3 | Training
4 | Health Products and Health Equipment | [11 empty] | Budget for Reporting Period* | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
5 | Medicines and Pharmaceutical Products | [10 empty] | 2. Total pharmaceutical & health product expenditures vs. budget | 4057423 | 0 | 4057423 |  | 4057423 | 0 | 4057423
6 | Procurement and Supply Management Costs | [10 empty] | 2a. Medicines and pharmaceutical products | 681439 | 0 | 681439 |  | 681439 | 0 | 681439
7 | Infrastructure and Other Equipment | [10 empty] | 2b. Health products and health equipment | 3375984 | 0 | 3375984 |  | 3375984 | 0 | 3375984
8 | Communication Materials
9 | Monitoring & Evaluation
10 | Living Support to Clients/Target Populations
11 | Planning and Administration
12 | Overheads
13 | Other
|  |  | TOTAL | 0 | 0 | 0 |  | 0 | 0 | 0
B- BREAKDOWN* BY PROGRAM ACTIVITY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period
# | Macro-category | Objectives | Service Delivery Area | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance
| Please Select… |  | please select…
| Please Select… |  | please select…
| Please Select… |  | Please select…
| Please Select… |  | Please select…
| Please Select… |  | Please select…
| Please Select… |  | Please select…
TOTAL |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
To add additional rows, right click the row number (Row 39 in a blank template) to the left of the row above the row for TOTAL and select copy, then over the same number, right click again and select Insert Copied Cells. WARNING: Inserting Rows without copying a row as described above will cause the formula in the variance column to become invalid and will mean the overall information will be inaccurate.
C- BREAKDOWN* BY IMPLEMENTING ENTITY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period
# | PR/SR | Name | Type of Implementing Entity | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance
| PR | UNOPS | Other Multilateral Organization
| SR | MCC | FBO
| SR | MMA | NGO/CBO/Academic
| SR | MRCS | NGO/CBO/Academic
| SR | VBDC | NGO/CBO/Academic
| SR | WHO | Other Multilateral Organization
|  |  | TOTAL | 0 | 0 | 0 |  | 0 | 0 | 0
To add additional rows, right click the row number (Row 51 in a blank template) to the left of the row above the row for TOTAL and select copy, then over the same number, right click again and select Insert Copied Cells. WARNING: Inserting Rows without copying a row as described above will cause the formula in the variance column to become invalid and will mean the overall information will be inaccurate.
* The sum of all three breakdowns should be equal (A- Budget Line-item, B- Program Activity, C- Implementing Entity).
** For the purposes of this report, the SDA Program management and administration should be included in the Supportive Environment Macro Category.
D- ADDITIONAL INFORMATION
Please disclose any relevant information concerning the information in the above tables. Refer to the Guidelines for Completing the Template if required.
E- DISBURSEMENTS BREAKDOWN BY IMPLEMENTING ENTITY |  |  |  | Cumulative Reporting Period
# | Name | Type of Implementing Entity | Cumulative Disbursements | Comments
Please Select…
Please Select…
Please Select…
Please Select…
Please Select…
|  | TOTAL | 0
Note on A32: Insert Number
Note on A45: Insert Number
Note on A69: Insert Number
Note on B27: This category should only be used as a last resort if there is a type of cost that absolutely cannot be allocated to another cost category
Note on C32: Please Remember to include the full name of the Objective. If an objective has more than 1 SDA, repeat the Objective Name on each row for the relevant SDA
Note on C69: If a Faith Based Organization is also a NGO or CBO. It should be selected as an FBO!
Note on D45: If a Faith Based Organization is also a NGO or CBO. It should be selected as an FBO!
Note on D75: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on E28: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on E39: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on E52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on E68: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on E69: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on F28: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on F39: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on F52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on G8: Start date for current period cannot be earlier than cumulative period
Note on G9: Start date for current period cannot be earlier than cumulative period
Note on G28: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on G39: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on G52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on H14: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on H32: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on H45: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on I13: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I18: Please ensure that the figure here agrees with the cumulative budget figure in the corresponding cell (H18) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I19: Please ensure that the figure here agrees with the cumulative budget figure in the corresponding cell (H17) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I28: Please ensure that: -the figure here agrees with the figure in the corresponding cells in Tables B and C (in this tab). If they do not the background color will be RED; and -the figure also agrees with the cumulative budget figure in the corresponding cell (H11) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I31: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I39: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on I44: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on J18: Please ensure that the figure here agrees with the cumulative cash outflow figure in the corresponding cell (I18) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on J19: Please ensure that the figure here agrees with the cumulative cash outflow figure in the corresponding cell (I17) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on J28: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on J39: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on J52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on K8: Start date for current period cannot be earlier than cumulative period
Note on K9: Start date for current period cannot be earlier than cumulative period
Note on K28: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on K39: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on K52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on L14: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on L32: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on L45: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.

## EFR TB Financial Data_3B (hidden)
SECTION 3B: TB FINANCIAL REPORTING FORM
Country |  | Union of Myanmar |  |  | PLEASE REFER TO THE "GUIDANCE FOR COMPLETION OF THE ENHANCED FINANCIAL REPORTING TEMPLATE" DOCUMENT TO ASSIST YOU IN COMPLETING THE TEMPLATE
Grant No. |  | MYN-S10-G07-M
PR |  | UNOPS |  |  | TO BE COMPLETED ONLY ONCE A YEAR EXCEPT AT MONTH 18 FOR PURPOSES OF PHASE 2 REVIEW
Currency |  | Please Select …
[6 empty] | dd-mm-yyyy |  |  |  | dd-mm-yyyy
|  |  |  | Current Reporting Period | Start Date: |  |  | Cumulative Reporting Period | Start Date:
[5 empty] | End Date: |  |  |  | End Date:
The end date for the current reporting period and cumulative reporting period must be the same
The "TOTAL" rows in Table A, B and C will have a RED background if the amounts in each table do not agree. If the Totals for each Table agrees, these rows will have a YELLOW background.
A- BREAKDOWN* BY EXPENDITURE CATEGORY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period |  |  |  | All amounts are in: | Budget for Reporting Period | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
# | Category |  |  | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance | 1. Total PR cash outflow vs. budget | 7276967.52 | 185234.85 | 7091732.67 |  | 7276967.52 | 185234.85 | 7091732.67
1 | Human Resources | [10 empty] | 1a. PR's total expenditures | 1637375.47 | 185234.85 | 1452140.62 |  | 1637375.47 | 185234.85 | 1452140.62
2 | Technical Assistance | [10 empty] | 1b. Disbursements to sub-recipients | 5639592.05 | 0 | 5639592.05 |  | 5639592.05 | 0 | 5639592.05
3 | Training
4 | Health Products and Health Equipment | [11 empty] | Budget for Reporting Period* | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
5 | Medicines and Pharmaceutical Products | [10 empty] | 2. Total pharmaceutical & health product expenditures vs. budget | 4057423 | 0 | 4057423 |  | 4057423 | 0 | 4057423
6 | Procurement and Supply Management Costs | [10 empty] | 2a. Medicines and pharmaceutical products | 681439 | 0 | 681439 |  | 681439 | 0 | 681439
7 | Infrastructure and Other Equipment | [10 empty] | 2b. Health products and health equipment | 3375984 | 0 | 3375984 |  | 3375984 | 0 | 3375984
8 | Communication Materials
9 | Monitoring & Evaluation
10 | Living Support to Clients/Target Populations
11 | Planning and Administration
12 | Overheads
13 | Other
|  |  | TOTAL | 0 | 0 | 0 |  | 0 | 0 | 0
B- BREAKDOWN* BY PROGRAM ACTIVITY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period
# | Macro-category | Objectives | Service Delivery Area | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance
| Please Select… |  | Please Select…
| Please Select… |  | Please Select…
| Please Select… |  | Please Select…
| Please Select… |  | Please Select…
| Please Select… |  | Please Select…
TOTAL |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
To add additional rows, right click the row number (Row 39 in a blank template) to the left of the row above the row for TOTAL and select copy, then over the same number, right click again and select Insert Copied Cells. WARNING: Inserting Rows without copying a row as described above will cause the formula in the variance column to become invalid and will mean the overall information will be inaccurate.
C- BREAKDOWN* BY IMPLEMENTING ENTITY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period
# | PR/SR | Name | Type of Implementing Entity | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance
| Please Select … |  | Please Select…
| Please Select … |  | Please Select…
| Please Select … |  | Please Select…
| Please Select … |  | Please Select…
| Please Select … |  | Please Select…
|  |  | TOTAL | 0 | 0 | 0 |  | 0 | 0 | 0
To add additional rows, right click the row number (Row 51 in a blank template) to the left of the row above the row for TOTAL and select copy, then over the same number, right click again and select Insert Copied Cells. WARNING: Inserting Rows without copying a row as described above will cause the formula in the variance column to become invalid and will mean the overall information will be inaccurate.
* The sum of all three breakdowns should be equal (A- Budget Line-item, B- Program Activity, C- Implementing Entity).
** For the purposes of this report, the SDA Program management and administration should be included in the Supportive Environment Macro Category.
D- ADDITIONAL INFORMATION
Please disclose any relevant information concerning the information in the above tables. Refer to the Guidelines for Completing the Template if required.
E- DISBURSEMENTS BREAKDOWN BY IMPLEMENTING ENTITY |  |  |  | Cumulative Reporting Period
# | Name | Type of Implementing Entity | Cumulative Disbursements | Comments
Please Select…
Please Select…
Please Select…
Please Select…
Please Select…
|  | TOTAL | 0
Note on A34: Insert Number
Note on A46: Insert Number
Note on A69: Insert Number
Note on B29: This category should only be used as a last resort if there is a type of cost that absolutely cannot be allocated to another cost category
Note on C34: Please Remember to include the full name of the Objective. If an objective has more than 1 SDA, repeat the Objective Name on each row for the relevant SDA
Note on C69: If a Faith Based Organization is also a NGO or CBO. It should be selected as an FBO!
Note on D46: If a Faith Based Organization is also a NGO or CBO. It should be selected as an FBO!
Note on D75: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on E30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on E40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on E52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on E68: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on E69: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on F30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on F40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on F52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on G8: Start date for current period cannot be earlier than cumulative period
Note on G30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on G40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on G52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on H16: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on H34: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on H46: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on I15: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I20: Please ensure that the figure here agrees with the cumulative budget figure in the corresponding cell (H18) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I21: Please ensure that the figure here agrees with the cumulative budget figure in the corresponding cell (H17) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I30: Please ensure that: -the figure here agrees with the figure in the corresponding cells in Tables B and C (in this tab). If they do not the background color will be RED; and -the figure also agrees with the cumulative budget figure in the corresponding cell (H11) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I33: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on I45: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on J20: Please ensure that the figure here agrees with the cumulative cash outflow figure in the corresponding cell (I18) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on J21: Please ensure that the figure here agrees with the cumulative cash outflow figure in the corresponding cell (I17) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on J30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on J40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on J52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on K8: Start date for current period cannot be earlier than cumulative period
Note on K30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on K40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on K52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on L16: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on L34: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on L46: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.

## EFR HIV AIDS Financial Data_3B (hidden)
SECTION 3B: HIV/AIDS FINANCIAL REPORTING FORM
Country |  | Union of Myanmar |  |  | PLEASE REFER TO THE "GUIDANCE FOR COMPLETION OF THE ENHANCED FINANCIAL REPORTING TEMPLATE" DOCUMENT TO ASSIST YOU IN COMPLETING THE TEMPLATE
Grant No. |  | MYN-S10-G07-M
PR |  | UNOPS |  |  | TO BE COMPLETED ONLY ONCE A YEAR EXCEPT AT MONTH 18 FOR PURPOSES OF PHASE 2 REVIEW
Currency |  | Please Select …
[6 empty] | dd-mm-yyyy |  |  |  | dd-mm-yyyy
|  |  |  | Current Reporting Period | Start Date: |  |  | Cumulative Reporting Period | Start Date:
[5 empty] | End Date: |  |  |  | End Date:
The end date for the current reporting period and cumulative reporting period must be the same
The "TOTAL" rows in Table A, B and C will have a RED background if the amounts in each table do not agree. If the Totals for each Table agrees, these rows will have a YELLOW background.
A- BREAKDOWN* BY EXPENDITURE CATEGORY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period |  |  |  | All amounts are in: | Budget for Reporting Period | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
# | Category |  |  | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance | 1. Total PR cash outflow vs. budget | 7276967.52 | 185234.85 | 7091732.67 |  | 7276967.52 | 185234.85 | 7091732.67
1 | Human Resources | [10 empty] | 1a. PR's total expenditures | 1637375.47 | 185234.85 | 1452140.62 |  | 1637375.47 | 185234.85 | 1452140.62
2 | Technical Assistance | [10 empty] | 1b. Disbursements to sub-recipients | 5639592.05 | 0 | 5639592.05 |  | 5639592.05 | 0 | 5639592.05
3 | Training
4 | Health Products and Health Equipment | [11 empty] | Budget for Reporting Period* | Actual Cash Outflow for Reporting Period | Variance | Reason for Variance | Cumulative Budget through period of Progress Update | Cumulative Actual Cash Outflow through period of Progress Update | Variance | Reason for Variance
5 | Medicines and Pharmaceutical Products | [10 empty] | 2. Total pharmaceutical & health product expenditures vs. budget | 4057423 | 0 | 4057423 |  | 4057423 | 0 | 4057423
6 | Procurement and Supply Management Costs | [10 empty] | 2a. Medicines and pharmaceutical products | 681439 | 0 | 681439 |  | 681439 | 0 | 681439
7 | Infrastructure and Other Equipment | [10 empty] | 2b. Health products and health equipment | 3375984 | 0 | 3375984 |  | 3375984 | 0 | 3375984
8 | Communication Materials
9 | Monitoring & Evaluation
10 | Living Support to Clients/Target Populations
11 | Planning and Administration
12 | Overheads
13 | Other
|  |  | TOTAL | 0 | 0 | 0 |  | 0 | 0 | 0
B- BREAKDOWN* BY PROGRAM ACTIVITY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period
# | Macro-category | Objectives | Service Delivery Area | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance
| Please Select… |  | Please Select…
| Please Select… |  | Please Select…
| Please Select… |  | Please Select…
| Please Select… |  | Please Select…
| Please Select… |  | Please Select…
TOTAL |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
To add additional rows, right click the row number (Row 39 in a blank template) to the left of the row above the row for TOTAL and select copy, then over the same number, right click again and select Insert Copied Cells. WARNING: Inserting Rows without copying a row as described above will cause the formula in the variance column to become invalid and will mean the overall information will be inaccurate.
C- BREAKDOWN* BY IMPLEMENTING ENTITY |  |  |  | Current Reporting Period |  |  |  | Cumulative Reporting Period
# | PR/SR | Name | Type of Implementing Entity | Budget | Expenditures | Variance | Reason for Variance | Cumulative Budget | Cumulative Expenditure | Variance | Reason for Variance
| Please Select … |  | Please Select…
| Please Select … |  | Please Select…
| Please Select … |  | Please Select…
| Please Select … |  | Please Select…
| Please Select … |  | Please Select…
|  |  | TOTAL | 0 | 0 | 0 |  | 0 | 0 | 0
To add additional rows, right click the row number (Row 51 in a blank template) to the left of the row above the row for TOTAL and select copy, then over the same number, right click again and select Insert Copied Cells. WARNING: Inserting Rows without copying a row as described above will cause the formula in the variance column to become invalid and will mean the overall information will be inaccurate.
* The sum of all three breakdowns should be equal (A- Budget Line-item, B- Program Activity, C- Implementing Entity).
** For the purposes of this report, the SDA Program management and administration should be included in the Supportive Environment Macro Category.
D- ADDITIONAL INFORMATION
Please disclose any relevant information concerning the information in the above tables. Refer to the Guidelines for Completing the Template if required.
E- DISBURSEMENTS BREAKDOWN BY IMPLEMENTING ENTITY |  |  |  | Cumulative Reporting Period
# | Name | Type of Implementing Entity | Cumulative Disbursements | Comments
Please Select…
Please Select…
Please Select…
Please Select…
Please Select…
|  | TOTAL | 0
Note on A34: Insert Number
Note on A46: Insert Number
Note on A69: Insert Number
Note on B29: This category should only be used as a last resort if there is a type of cost that absolutely cannot be allocated to another cost category
Note on C34: Please remember to include the full name of the objective. If an objective has more than 1 SDA, repeat the objective name on each row for the relevant SDA
Note on C69: If a Faith Based Organization is also a NGO or CBO. It should be selected as an FBO!
Note on D46: If a Faith Based Organization is also a NGO or CBO. It should be selected as an FBO!
Note on D75: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on E30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on E40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on E52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on E68: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on E69: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on F30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on F40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on F52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on G8: Start date for current period cannot be earlier than cumulative period
Note on G30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on G40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on G52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on H16: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on H34: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on H46: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on I15: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I20: Please ensure that the figure here agrees with the cumulative budget figure in the corresponding cell (H18) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I21: Please ensure that the figure here agrees with the cumulative budget figure in the corresponding cell (H17) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I30: Please ensure that: -the figure here agrees with the figure in the corresponding cells in Tables B and C (in this tab). If they do not the background color will be RED; and -the figure also agrees with the cumulative budget figure in the corresponding cell (H11) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on I33: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on I45: The Cumulative Period should be from the beginning of the grant up to the end of the current reporting period.
Note on I52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on J20: Please ensure that the figure here agrees with the cumulative cash outflow figure in the corresponding cell (I18) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on J21: Please ensure that the figure here agrees with the cumulative cash outflow figure in the corresponding cell (I17) in section "PR_Total PR Cash Outflow_3A). If they do not the background color will be ORANGE.
Note on J30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on J40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on J52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on K8: Start date for current period cannot be earlier than cumulative period
Note on K30: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables B and C. If they do not the background color will be RED
Note on K40: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and C. If they do not the background color will be RED
Note on K52: Please ensure that the figure here agrees with the figure in the corresponding cells in Tables A and B. If they do not the background color will be RED
Note on L16: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on L34: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.
Note on L46: Please be as specific as possible when describing the Reason for the Variances. Refer to the Guidance Document for additional information.

## PR_Procurement Info_4
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | MYN-S10-G07-M
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 1
Progress Update - Period Covered: | Beginning Date: | 2011-01-01 | End Date: | 2011-03-31
Progress Update - Number: | 1
Section 4: Procurement and Supply Management
Comments
1a. Have you updated the Price Quality Reporting (PQR) with the required information on the pharmaceuticals and health products received during the period covered by this PU/DR’ (if applicable)? If health products procurement information has not been entered into the PQR, please explain why. ! For further guidance on PQR data entry, please refer to the guidelines. |  |  | No | India Procurement Office will update the PQR once the procurement action is completed. No such action has been completed yet in this quarter.
2. Based on the most up-to-date stock situation, are there any risks of stockouts of key pharmaceuticals & health products at the central level in the next period of implementation? If yes, please comment. |  |  | No | ACTs and RDTs are expected to be delivered by July-Aug 2011. At present there is enough stcok of ACTs and RDTs in the VBDC store to cover this period.
3. Comment on additional issues related to the procurement and supply management of pharmaceuticals and health products
LLINs are arriving on May 16 2011, expected to be distributed to townships by end of May.

## PR_Cash Reconciliation_5A
On-going Progress Update and Disbursement Request
DISBURSEMENT REQUEST PERIOD
Grant number: |  | MYN-S10-G07-M |  |  |  | ! A Statement of Sources and Uses of Funds (SSUF) is to be provided by PR along with the PUDR form
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 1
Progress Update - Period Covered: |  | Beginning Date: | 2011-01-01 | End Date: | 2011-03-31
Progress Update - Number: |  | 1
Currency: |  | USD
Section 5: Cash Reconciliation and Disbursement Request
A: CASH RECONCILIATION FOR PERIOD COVERED BY PROGRESS UPDATE
1. Cash Balance: Beginning of period covered by Progress Update (line 10 from Cash Reconciliation section of the period covered by the previous Progress Update):
Add: | 2. Cash received by the PR from the Global Fund during the period covered by this progress update: | [5 empty] | 7642241
3. Cash disbursed to third parties by the Global Fund on behalf of the PR during the period covered by this progress update:
4. Interest received on bank account
5. Revenue from income-generating activities (if applicable)
| 6. Other income, if applicable (e.g. income from disposal of fixed assets, tax refunds) | [6 empty] | 7642241
Less: | 7. Total cash outflow during period covered by Progress Update (value entered in Section 3A "Total cash outflow"): | [5 empty] | 185234.85
8. Net exchange rate gains/losses (gains should be shown with a minus sign; losses should be shown with a plus sign)
| 9. Reconciliation adjustments (gains should be shown with a minus sign; losses should be shown with a plus sign) | [6 empty] | 185234.85
10. Cash Balance: End of period covered by Progress Update: | [7 empty] | 7457006.15
Explanation of reconciliation adjustments (line 9)
! An explanation must be provided if there have been any adjustments.

## PR_Disbursement Request_5B
On-going Progress Update and Disbursement Request
DISBURSEMENT REQUEST PERIOD
Grant number: |  |  |  |  | MYN-S10-G07-M
Progress Update - Reporting Period: |  |  |  |  | Cycle: | Quarter | Number: | 1
Progress Update - Period Covered: |  |  |  |  | Beginning Date: | 2011-01-01 | End Date: | 2011-03-31
Progress Update - Number: |  |  |  |  | 1
Currency: |  |  | USD
Section 5: Cash Reconciliation and Disbursement Request
B: DISBURSEMENT REQUEST
Total forecasted net cash expenditures by the Principal Recipient for the period immediately following the period covered
by the Progress Update:
1. Period beginning date: |  |  |  | 2011-04-01 |  | end date: | 2011-06-30 |  | approved budget amount: | 845047 | forecasted amount: | 845047
2a. Cash buffer period (by default)
(cash "buffer") beginning date: |  |  |  | 2011-07-01 |  | end date: | 2011-09-30 |  | approved budget amount: | 925144 | forecasted amount: | 925144
PR Total Forecast
2b. Additional "buffer" (discretionary, select only if there is a prior agreement with the FPM) (1) | [12 empty] | 1770191
cash "buffer" agreed with FPM (2) |  | Select
(cash "buffer") beginning date |  |  |  | 2011-10-01 |  | end date: |  |  | approved budget amount: |  | forecasted amount:
(1) Additional Cash buffer can be requested if the next PU/DR report will contain a completed EFR report or a completed Annex on SR financials, requested by the Secretariat, or if there are any additional GF-specific requirements that cannot be delivered within 45 days. An agreement in principal from the FPM should be obtained prior to requesting an additional cash buffer.
(2) When the additional (cash "buffer" ) period is 1 or 2 months, the approved budget and forecasted amounts should be calculated as prorated values for the period following the regular buffer period.
Please explain any significant variance (based on your judgment) between the forecasted amounts and the amounts as per approved budgets. Please specify the main factors and related amounts that are the major drivers of the variance. NB. Consider the following items when providing the analysis. - Expected timing of payments for any significant budgetary items, - Impact of existing cash balance at SR levels - Current confirmed commitments to be paid during disbursement request period - Current/expected unit prices compared to those in the budget - Change in quantities compared to budget - Exchange rates and inflation - Linkage between budget absorption and programmatic performance to-date. ! The forecast should include any existing commitments (eligible under this grant) as of the end of the reporting period and which are likely to be paid during the disbursement period
Less: | 3. Cash Balance: End of period covered by Progress Update (number 10 from PR Cash Reconciliation sheet): | [10 empty] | 7457006.15
4. Cash "in transit" disbursed to the PR:
| 5. Cash "in transit" disbursed to third parties by the Global Fund on behalf of the PR | [11 empty] | 7457006.15
6. PR's Disbursement Request to the Global Fund for the period immediately following the period covered by the Progress Update, plus additional period (cash buffer): | [12 empty] | 0
7. Does the PR's Disbursement Request include funds for health product procurement? | [7 empty] | Yes
8. Exchange Rate (used to translate local currency into grant currency) | [7 empty] | Name of local currency, date and source of the exchange rate, and other comments (if appropriate)
| - used to convert Opening Cash Balance |  |  |  |  | Yes
| - used to convert Closing Cash Balance |  |  |  |  | No |  | MMK, UNORE
| - used to convert Total Cash Outflow for the Progress Update Period |  |  |  |  | Yes |  | MMK, UNORE

## PR_Overall Performance_6
On-going Progress Update and Disbursement Request
PROGRESS UPDATE PERIOD
Grant number: | MYN-S10-G07-M
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 1
Progress Update - Period Covered: | Beginning Date: | 2011-01-01 | End Date: | 2011-03-31
Progress Update - Number: | 1
Section 6: Overall Performance
A. PR's Overall Self-Evaluation of Grant Performance (including a summary of how financial performance is linked to programmatic achievements)
! The self-evaluation should be undertaken by taking into account programmatic achievements, financial performance and program issues in various functional areas (M&E, Finance, Procurement, and Program Management, including management of sub-recipients). See Guidelines for more detailed guidance.
There was a low burn-rate on PR expenditures of 2.5 % due to little or no implementation as result of delayed disbursements, recruitment and approval of finance manuals. However, some activities took place using funding from other sources (3DF). During this reporting period, 4 out of 5 indicators/results due for reporting were reported, with a performance of between 35%-100%. Specifically, the results of number of RDTs used and tested showed good performance (23,106 results vs. 40,450 target), representing 57%. However this does not include 112,693 RDTs tests done and read, using 3-DF resources by the National Malaria Control Programme, whose targets are tied to the current grant. Notably, remarkable performance was noted under SDA: prompt effective anti-malarial treatments; with number of people with confirmed Malaria treated with recommended ACT showing 7039 results vs. 10750 targets; representing 65% of projected target. This however does not include 43,667 patients treated with ACT by NMCP using 3DF resources whose targets are tied to the current grant. The outstanding performance on the number of people with Malaria treated with chloroquine (results 8961 vs. 9000 targets), representing 100%. However this does not include 35,304 people with Malaria treated with chloroquine using 3DF funding during the reporting period, whose targets are tied to the current grant. Lastly, the poor performance on the training indicator (number of staff trained and retrained) during this reporting period may be attributed to the delays in approving finance manuals. It is envisaged that significant improvements would be made given the revision of all SRs' workplans to ensure catch-up on deliverables in the remaining quarters of the year. M&E: Key M&E positions in the M&E Unit have been filled including International M&E Specialist, three National disease specific M&E Officers and National Database Specialist. Essential reporting tools and guidelines have been developed and finalized including internal tools: Validation Tools, Checklists and External tools: DQA Manual, Guidelines for Completing Reporting Forms; Quarterly Reporting Forms/Templates. The PR has since commenced PR/SR Capacity Building through PR internal training on Global Fund structure and technical reporting demands and requirements. The first in a series of planned orientation of Sub-recipients has been completed, including on–site support to SRs in completing the 1st Quarter Reports to UNOPS/PR. A central level M&E workshop is planned for June 2011 to further address GF reporting demands and requirements and strengthen SRs' M&E capacities as well as the commencement of data quality assurance activities on an ongoing basis for selected indicators and reporting periods. The 1st Prototype of PR Programmatic database & FFM Database has been developed. Finance: Recruitments in the Finance Team have been completed, including the FFAs for the Funds Flow Mechanism for the National Programmes. The first 13 FFAs have been deployed in early May to the field locations and additional 12 FFAs are deployed in their respective field locations in mid-May. During the first week of April three day training with the National Programmes was held. The meeting explained the full FFM scheme, responsibility of the National Programmes as SRs and more. The Financial Management Policy and Procedures Manual (FPPM) was approved 2nd May 2011. The PR has embarked on a series of SR Capacity Building actions through ongoing trainings/workshops and support visits with SRs. The PR envisages to commence Financial Monitoring of SRs (part of the Capacity Building function) beginning this quarter. The Global Fund has approved that no LNGO SR will be on Zero Cash Policy at the beginning of implementation. The PR has developed tools, both internal and external: SR monitoring plans, monitoring checklist, risk framework and monitoring methodology completed; including development of verification and certification checklists. Logistics/Procurement: All Procurement and Logistics Unit positions are in place. However it is envisaged that the International QA/QC Officer will be recruited after the LFA assessment in May to allow the PR to conduct procuerment in Year 2 for the Round 9 grant. The PR has put in place and commenced a series of ongoing trainings of SRs (Local NGOs) focused on general topics: Procurement, Asset Management and Supply Chain Management. Prior to this internal training on UNOPS Procurement Rules & Regulations and GF quality assurance policy was conducted for PR staff. Discussion on standardization of reporting forms is in progress with STC and SRs. LMIS is under preparation and will be submitted by 30 June 2011. Training and certification by the GF approved PSM expert is being conducted from May 15. The PR has Completed Survey of the current public sector storage facilities. The Renovation plan was submitted to GF. In principle approval received for stores in Yangon. State /Region Level plans are still under discussion. Initial draft of LLIN distribution plan and annexes were submitted on March 21st. Three (3) S/D level warehouses are under construction using funding from, “Japan’s Grassroots Grant Assistance”. Construction will start after signing of the Agreement with MOH. For the other 3 warehouses funded by the Japanese Embassy's grant, an SR (PGK) has since submitted the proposal to the Japanese Embassy for necessary approval from Tokyo. Renovation: An RFQ has been issued for selection of consultant for designing. For selected lab and surgical items to be procured locally, RFQ issued, evaluation completed and submitted to Save the Children for concurrence. Four more RFQs/ITB (national) are to be issued in mid-May for majority of laboratory and surgical items. IPO is procuring the items not available locally.
B. Planned Changes in the Program, if any
VBDC is reviewing its Tsp coverage and changes are foreseen to be made in Q2.
C. External factors beyond the control of the Principal Recipient that have impacted or may impact the Program

## PR_Cash Request_7A&B
On-going Progress Update and Disbursement Request
GENERAL GRANT INFORMATION
Country: | Union of Myanmar
Disease: | Malaria
Grant number: | MYN-S10-G07-M
Principal Recipient: | UNOPS
Program Start Date: | 2011-01-01
Currency: | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 1
Progress Update - Period Covered: | Beginning Date: | 2011-01-01 | End Date: | 2011-03-31
Progress Update - Number: | 1
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: | Cycle: | Quarter | Number: | 2
Disbursement Request - Period Covered: | Beginning Date: | 2011-04-01 | End Date: | 2011-06-30
Disbursement Request - Number: | 2
Section 7: Cash Request and Authorization
A: CASH REQUEST
On behalf of the PR, the undersigned hereby requests the Global Fund to disburse funds under the above-referenced Grant Agreement as follows:
1. Cash amount requested from the Global Fund (from line 14 – “PR's Disbursement Request” in the tab “PR_Disbursement Request_4B”), in grant currency |  | 0
2. Amount requested in words (in: USD):
B: AUTHORIZATION
The undersigned acknowledges that: (i) all the information (programmatic, financial, or otherwise) provided in this Progress Update and Disbursement Request is complete and accurate; (ii) funds disbursed in accordance with this request shall be deposited in the bank account specified in block 9 of the face sheet of the Grant Agreement unless otherwise specified herein; and (iii) funds disbursed under the Grant Agreement shall be used in accordance with the Grant Agreement.
Signed on behalf of the Principal Recipient: (signature of Authorized Designated Representative)
Name: | Dr. Attila Molnar
Title: | Programme Coordinator, UNOPS, Principal Recipient for the Global Fund to Fight AIDS, Tuberculosis and Malaria
Date and Place: | 20 May 2011, Yangon, Myanmar
NB: Please ensure that section 7C Bank Details on the following page is completed, if (1) this is a split disbursement (i.e. disbursement going to more than one recipient) or (2) if there have been changes to the bank details since the previous disbursement.

## PR_Bank Details_7C
On-going Progress Update and Disbursement Request
NB: This page should be completed if (1) this is a split disbursement (i.e. disbursement going to more than one recipient) or (2) if there have been changes to the bank details since the previous disbursement.
7C: Bank Account Details
Disbursement Request Period
Summary
|  | Beneficiary Name | Amount in grant currency
| Payee 1 - Principal Recipient: | 0 | 0
| Payee 2: | 0 | 0
| Payee 3: | 0 | 0
| Payee 4: | 0 | 0
| Total |  | 0
Payee 1:
| Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
Routing Instructions:
Payee 2:
| Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
Routing Instructions:
Payee 3:
| Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
Routing Instructions:
Payee 4:
| Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
Routing Instructions:

## PR_Annex_SR-Financials
On-going Progress Update and Disbursement Request
Annex to PU/DR - Sub-recipient financial information - FOR DISCRETIONARY COMPLETION, UPON THE SECRETARIAT'S REQUEST
Has the Secretariat requested the PR to complete this Annex for this reporting period? | [7 empty] | No
Grant number: |  |  |  |  | MYN-S10-G07-M
Progress Update - Reporting Period: |  |  |  |  | Cycle: | Quarter |  | Number: | 1
Progress Update - Period Covered: |  |  |  |  | Beginning Date: | 2011-01-01 |  | End Date: | 2011-03-31
Progress Update - Number: |  |  |  |  | 1
Currency: |  |  | USD
Name of Entity | Type of Implementing Entity | Date of Most Recent Disbursement to SR |  | Budget for Reporting Period* | Disbursed during Reporting Period* |  | Cumulative Budget through period of this Progress Update* | Cumulative Disbursed through period of this Progress Update* | Cumulative Actual Expenditure through period covered by this Progress Update | Cash balance at the end of the period covered by this Progress Update | Variance between Latest Cumulative Expenditure Reported and Cumulative Budget | Expenditure Verified by PR (YES/NO) | PR's explanation of variance (1) between cumulative budget and cumulative expenditure and (2) between cumulative disbursement and cumulative expenditure (mandatory for amounts above $50,000 or equivalent and with more than 10% variance)
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | Yes
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
TOTAL |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0
*TOTAL amount for these columns should reconcile with relevant amounts under "1b Disbursed to Sub Recipients" in Section 3A"
** Where the number of SRs is significant (over 10), SRs with small budgets (less than $50,000 cumulative each) do not need to be reported separately and the figures can be aggregated in a group called "Other Minor SRs"

## Checklist
List of supporting documents for PU/DR review
This checklist is included for information and not for completion.
List of Latest Approved Documents by functional area | To be made available to the LFA by the PR | To be submitted by the LFA to the Secretariat | Comments
M&E
Performance Framework | x
M&E Plan | x
Survey results | x |  | For Impact/Outcome indicators
M&E Systems Strengthening Assessment | x |  | If newly available during the reporting period.
Other M&E assessments done by partners to assess data quality and M&E system issues. | x |  | If newly available during the reporting period.
Procurement
Consumption reports for pharmaceuticals and health products | x
Supplier invoices | x
PSM Plan | x
Stock level reports | x
Finance
Approved budgets | x |  | For the periods covered by Progress Update and Disbursement Request, including the buffer period.
Statement of sources and uses of funds (Cash flow statement) | x | x | See guidance on SSUF content and format in the guidelines.
Cash books | x
General Ledger | x
Cash forecasts | x
Bank statements | x
Bank Reconciliations | x
Annual PR Audit Report, Financial Statements, Management Letters and Responses (if Due) | x | x
Annual SR Audit Report, Financial Statements, Management Letters and Responses (if Due) | x
General Management
Grant Agreement (including Annex A and subsequent implementation letters) | x
Workplan | x

## LFA_Programmatic Progress_1A
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office:
GENERAL GRANT INFORMATION
Country: |  | Union of Myanmar
Disease: |  | Malaria
Grant Number: |  | MYN-S10-G07-M
Principal Recipient: |  | UNOPS
Program Start Date: |  | 2011-01-01
Currency: |  | USD
PROGRESS UPDATE PERIOD
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 1
Progress Update - Period Covered: |  | Beginning Date: | 2011-01-01 | End Date: | 2011-03-31
Progress Update - Number: |  | 1
DISBURSEMENT REQUEST PERIOD
Disbursement Request - Disbursement Period: |  | Cycle: | Quarter | Number: | 2
Disbursement Request - Period Covered: |  | Beginning Date: | 2011-04-01 | End Date: | 2011-06-30
Disbursement Request - Number: |  | 2
TERMS AND ACRONYMS USED IN THIS PROGRESS REVIEW AND DISBURSEMENT RECOMMENDATION HAVE THE MEANING GIVEN TO THEM IN THE GRANT AGREEMENT RELATING TO THE ABOVE GRANT
Section 1: LFA Review and Verification of the Principal Recipient's Programmatic Progress
Note: The table below should contain those Impact/Outcome indicators that are (1) due for reporting during the current year of a grant and (2) those reporting on which is overdue from the previous periods.
A. Impact / Outcome Indicators | [12 empty] | A. Impact / Outcome Indicators
Impact / Outcome | Indicator Description |  |  |  | Year of Target | Intended Target (from Attachment) | Report Due Date | Actual Result (as reported by PR) | Data Source of Results | Verification Method | Verified Result | LFA comments on (a) verified result, (b) source of information used by the PR to report results, including the status of completion of surveys and other methods to measure Impact/Outcome, as applicable, | Impact / Outcome | Indicator Description | Year of Target | Intended Target (from Attachment) | Report Due Date | Actual Result (as reported by PR) | Data Source of Results
Outcome | Percentage of households with at least one LLIIN/ITN |  |  |  | 2011 | 0.53 | 31-12-2011 | - | Household survey |  |  |  | Outcome | Percentage of households with at least one LLIIN/ITN | 2011 | 0.53 | 31-12-2011 | - | Household survey
Outcome | Percentage of population at risk sleeping under an LLIN/ITN the previous night |  |  |  | 2011 | To be determined (TBD) | 31-12-2011 | - | Household survey |  |  |  | Outcome | Percentage of population at risk sleeping under an LLIN/ITN the previous night | 2011 | To be determined (TBD) | 31-12-2011 | - | Household survey
Outcome | Proportion of confirmed malaria cases treated in accordance with national malaria treatment guidelines within 24 hrs of onset of symptoms |  |  |  | 2011 | 0.3 | 31-12-2011 | - | VBDC |  |  |  | Outcome | Proportion of confirmed malaria cases treated in accordance with national malaria treatment guidelines within 24 hrs of onset of symptoms | 2011 | 0.3 | 31-12-2011 | - | VBDC
#REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## LFA_Programmatic Progress_1B
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  |  | MYN-S10-G07-M
Progress Update - Reporting Period: |  |  | Cycle: | Quarter | Number: | 1
Progress Update - Period Covered: |  |  | Beginning Date: | 2011-01-01 | End Date: | 2011-03-31
Progress Update - Number: |  |  | 1
Note: All programmatic indicators contained in the current Performance Framework should be listed, regardless of whether there are targets/results for the period covered by the Progress Update or whether the targets have been met in previous periods.
B. Programmatic Indicators | [15 empty] | B. Programmatic Indicators
Objective No. | Indicator No. | Indicator Description |  |  |  |  | Tied to | Targets cumulative? | Top 10 indicator? | Intended Target to date (from PF) | Actual Result to date (as reported by PR) | Verification Method | Verified Result | % achievement (Please calculate as appropriate) | LFA analysis on progress to date and any variance between targets and results, and any other comments (this should not be a “Copy and Paste” of the reasons provided by the PR) | Objective No. | Indicator No. | Indicator Description | Tied to | Targets cumulative? | Top 10 indicator? | Intended Target to date (from PF) | Actual Result to date (as reported by PR)
1 | 1.1 | Number of LLINs distributed free of charge for people at risk |  |  |  |  | Current grant | Y-cumulative annually | Yes - Top 10 | [6 empty] | 1 | 1.1 | Number of LLINs distributed free of charge for people at risk | Current grant | Y-cumulative annually | Yes - Top 10
1 | 1.3 | Number of mosquito nets treated with insecticide |  |  |  |  | Current grant | Y-cumulative annually | Yes - Top 10 | [6 empty] | 1 | 1.3 | Number of mosquito nets treated with insecticide | Current grant | Y-cumulative annually | Yes - Top 10
2 | 2.1 | Number of blood slides taken and examined |  |  |  |  | GF and other donors | Y-cumulative annually | No | [6 empty] | 2 | 2.1 | Number of blood slides taken and examined | GF and other donors | Y-cumulative annually | No
2 | 2.2 | Number of rapid diagnostic testes done and read |  |  |  |  | GF and other donors | Y-cumulative annually | No | 40450 | 23106 |  |  |  |  | 2 | 2.2 | Number of rapid diagnostic testes done and read | GF and other donors | Y-cumulative annually | No | 40450 | 23106
2 | 2.3 | Percentage of assessed malaria microscopists who met minimum national competency level |  |  |  |  | Current grant | N-not cumulative | No | [6 empty] | 2 | 2.3 | Percentage of assessed malaria microscopists who met minimum national competency level | Current grant | N-not cumulative | No
2 | 2.4 | Number of people with confirmed malaria treated with recommended ACT (disaggrated by age group and sex) |  |  |  |  | GF and other donors | Y-cumulative annually | Yes - Top 10 | 10750 | 7039 |  |  |  |  | 2 | 2.4 | Number of people with confirmed malaria treated with recommended ACT (disaggrated by age group and sex) | GF and other donors | Y-cumulative annually | Yes - Top 10 | 10750 | 7039
2 | 2.5 | Number of people with malaria (probable and confirmed) treated with chloroquine (disaggrated by age group and sex) |  |  |  |  | GF and other donors | Y-cumulative annually | Yes - Top 10 | 9000 | 8961 |  |  |  |  | 2 | 2.5 | Number of people with malaria (probable and confirmed) treated with chloroquine (disaggrated by age group and sex) | GF and other donors | Y-cumulative annually | Yes - Top 10 | 9000 | 8961
2 | 2.6 | Percentage of health facilities with no reported stock outs of nationally recommended antimalarial drugs lasting more than 1 week at any time during the past 3 months |  |  |  |  | GF and other donors | N-not cumulative | No | [6 empty] | 2 | 2.6 | Percentage of health facilities with no reported stock outs of nationally recommended antimalarial drugs lasting more than 1 week at any time during the past 3 months | GF and other donors | N-not cumulative | No
2 | 2.7 | Percentage of health care providers who provide antimalarial treatment according to national malaria treatment guidelines among those surveyed (disaggrated by categories of providers) |  |  |  |  | GF and other donors | N-not cumulative | No | [6 empty] | 2 | 2.7 | Percentage of health care providers who provide antimalarial treatment according to national malaria treatment guidelines among those surveyed (disaggrated by categories of providers) | GF and other donors | N-not cumulative | No
4 | 4.1 | Number of village health volunteers trained and supported for malaria prevention and control |  |  |  |  | GF and other donors | Y-cumulative annually | Yes - Top 10 | 224 | 0 |  |  |  |  | 4 | 4.1 | Number of village health volunteers trained and supported for malaria prevention and control | GF and other donors | Y-cumulative annually | Yes - Top 10 | 224 | 0
5 | 5.1 | Number of health staff trained and retrained |  |  |  |  | GF and other donors | Y-cumulative annually | Yes - Top 10 | 129 | 45 |  |  |  |  | 5 | 5.1 | Number of health staff trained and retrained | GF and other donors | Y-cumulative annually | Yes - Top 10 | 129 | 45
#REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
[7 empty] | Select | Select | Select | - | - | [7 empty] | Select | Select | Select | - | -
C LFA comments on data quality and reporting issues (!) This section should contain any common issues and/or additional information related to data quality and reporting on the programmatic indicators which are not covered in 'LFA analysis on progress to date and any variance between targets and results'

## LFA_Grant Management_2
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | MYN-S10-G07-M
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 1
Progress Update - Period Covered: | Beginning Date: | 2011-01-01 | End Date: | 2011-03-31
Progress Update - Number: | 1
Section 2: Grant Management
A. PR & LFA COMMENTS ON THE FULFILLMENT OF OUTSTANDING CONDITIONS PRECEDENT AND/OR SPECIAL CONDITIONS UNDER THE GRANT AGREEMENT
! This table should contain a full text of the CP and/or other special conditions due for fulfilment during this period or outstanding from previous periods.
! Some Special Conditions may apply to more than one period of grant implementation. Their fulfilment during one period does not automatically imply fulfilment in subsequent periods. The LFA should verify that the status of such conditions is reported by the PR during each period concerned.
! If a Condition Precedent that was previously fulfilled is re-opened due to new circumstances, and the issue addressed by this condition is considered critical, the issue should be disclosed by the LFA in the Section 4 LFA Findings and Recommendations. At the discretion of the Fund Portfolio Manager, the issue may be followed up through the management actions assigned by the Global Fund to the PR.
|  | PR SECTION | LFA SECTION
Conditions Precedent and/or other special conditions |  | Status | Status | Analysis (this should not be a "Copy and Paste" of the comments provided by the PR)
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF!
#REF! |  | #REF!
#REF! |  | #REF!
#REF! |  | #REF!
B. PR & LFA REVIEW OF PROGRESS ON IMPLEMENTATION OF OUTSTANDING MANAGEMENT ACTIONS FROM PREVIOUS DISBURSEMENTS
! This table should contain all issues raised in the last Management Letter from the Global Fund or outstanding from previous Management Letters, and comment on the progress.
Global Fund Management Actions |  | LFA Review of PR Progress on Global Fund Management Actions
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
C. PR & LFA COMMENTS ON ANNUAL GRANT REPORTING REQUIREMENTS
This table should contain the due date for the report due for submission. If a report is overdue, indicate the original due date and explain the reason for delay.
| PR SECTION |  | LFA SECTION
Required Documentation | Due date | Status | Due date | Status | Comments
PR Audit Report | #REF! | #REF!
Enhanced Financial Reporting (EFR) | #REF! | #REF!

## LFA_Total PR Cash Outflow_3A
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | MYN-S10-G07-M
Progress Update - Reporting Period: | Cycle: | Quarter |  | Number: | 1
Progress Update - Period Covered: | Beginning Date: | 2011-01-01 |  | End Date: | 2011-03-31
Progress Update - Number: | 1
Currency: | USD
Section 3A: Total PR Cash Outflow
LFA-VERIFIED TABLES ON TOTAL PR CASH OUTFLOW
! For RCC grants the cumulative section of the table below should contain cumulative amount from the start of the RCC and not from the start of Phase 1 of the program.
| LFA-Verified Budget for Reporting Period | LFA-Verified Actual for Reporting Period | Variance | LFA Analysis of Variance |  | LFA-Verified Cumulative Budget through period of Progress Update | LFA-Verified Actual through period of Progress Update | Variance | LFA Analysis of Variance | All amounts are in: | LFA-Verified Budget for Reporting Period | LFA-Verified Actual for Reporting Period | Variance | LFA Analysis of Variance | LFA-Verified Cumulative Budget through period of Progress Update | LFA-Verified Actual through period of Progress Update | Variance | LFA Analysis of Variance
1. Total cash outflow vs. budget | 7276967.52 | 185234.85 | 7091732.67 |  |  | 7276967.52 | 185234.85 | 7091732.67 |  | 1. Total cash outflow vs. budget | 7276967.52 | 185234.85 | 7091732.67 |  | 7276967.52 | 185234.85 | 7091732.67
1a. PR's total expenditures | 1637375.47 | 185234.85 | 1452140.62 |  |  | 1637375.47 | 185234.85 | 1452140.62 |  | 1a. PR's total expenditures | 1637375.47 | 185234.85 | 1452140.62 |  | 1637375.47 | 185234.85 | 1452140.62
1b. Disbursements to sub-recipients | 5639592.05 | 0 | 5639592.05 |  |  | 5639592.05 | 0 | 5639592.05 |  | 1b. Disbursements to sub-recipients | 5639592.05 | 0 | 5639592.05 |  | 5639592.05 | 0 | 5639592.05
| LFA-Verified Budget for Reporting Period | LFA-Verified Actual for Reporting Period | Variance | LFA Analysis of Variance |  | LFA-Verified Cumulative Budget through period of Progress Update | LFA-Verified Actual through period of Progress Update | Variance | LFA Analysis of Variance |  | LFA-Verified Budget for Reporting Period | LFA-Verified Actual for Reporting Period | Variance | LFA Analysis of Variance | LFA-Verified Cumulative Budget through period of Progress Update | LFA-Verified Actual through period of Progress Update | Variance | LFA Analysis of Variance
2. Pharmaceuticals & health product expenditures vs. budget | 4057423 | 0 | 4057423 |  |  | 4057423 | 0 | 4057423 |  | 2. Pharmaceuticals & health product expenditures vs. budget | 4057423 | 0 | 4057423 |  | 4057423 | 0 | 4057423
2a. Medicines and pharmaceutical products | 681439 | 0 | 681439 |  |  | 681439 | 0 | 681439 |  | 2a. Medicines and pharmaceutical products | 681439 | 0 | 681439 |  | 681439 | 0 | 681439
2b. Health products and health equipment | 3375984 | 0 | 3375984 |  |  | 3375984 | 0 | 3375984 |  | 2b. Health products and health equipment | 3375984 | 0 | 3375984 |  | 3375984 | 0 | 3375984
* If LFA-entered data differs from PR's figures, the respective cells will change colour automatically
3. Indicate any expenditures (incurred or forecasted) that should not be financed by the Global Fund

## LFA_EFR Review_3B
LFA review of Enhanced Financial Reporting template
LFA Organization / Responsible office:
GENERAL GRANT INFORMATION
Country: |  |  | Union of Myanmar
Disease: |  |  | Malaria
Grant Number: |  |  | MYN-S10-G07-M
Principal Recipient: |  |  | UNOPS
Program Start Date: |  |  | 2011-01-01
Currency: |  |  | USD
Section 3B: ENHANCED FINANCIAL REPORTING PERIOD
Current Period |  |  | Beginning Date: | End Date:
Cumulative Period |  |  | Beginning Date: | End Date:
1. CHECKLIST
The following information provided by the Principal Recipient in its EFR has been checked. |  |  |  |  | Comments if any:
| Select | The template has been fully completed.
1
| Select | The total figures in Tables A, B and C are equal.
2
| Select | The reporting dates are correct for both current period and cumulative period.
3
| Select | The total budget figure is accurate based on existing approved budgets.
4
| Select | The PR expenditure in Table C is consistent with PR expenditure for the same period as provided in the Progress Updates/Disbursements Request (PU/DR).
5
| Select | The total expenditure is supported by appropriate documentation ( PR expenditure reports, bank reconciliations, SR expenditure reports to PR etc.) or reasonable assumptions.
6
2. COMPLETION OF THE TEMPLATE
Comments on the process, assumptions and supporting documentation used by the PR to complete the template. (If space is insufficient, please provide comments in an addendum)
3. VARIANCE ANALYSIS
Comments on the explanations for variances provided by the PR (LFA can also provide comment directly on the EFR template completed by the PR)
Signed on behalf of the LFA:
Name:
Title:
Date and Place:

## LFA_Procurement Info_4
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: | MYN-S10-G07-M
Progress Update - Reporting Period: | Cycle: | Quarter |  | Number: |  | 1
Progress Update - Period Covered: | Beginning Date: | 2011-01-01 |  | End Date: |  | 2011-03-31
Progress Update - Number: | 1
Section 4: LFA-verified Procurement and Supply Management Information
| PR's response | LFA's response | LFA Comments/Analysis
1a. Has the PR updated the Price Quality Reporting (PQR) with the required information on the pharmaceuticals and health products received during the period covered by this PU/DR’ (if applicable)? (If health products procurement information has not been entered into the PQR, please explain why in comments box) | No | Select
1b. Value of Pharmaceuticals and Health Products in the PQR (6 categories only)
(!) This table is included in the PU/DR form with the aim to improve completeness of information in the PQR system and not for comparing PQR amounts vis-à-vis expenditure per se. NB: PQR and expenditure amounts on health products may not be equal due to a timelag between payments and delivery of pharmaceuticals/health products. (!) For further guidance on PQR data entry, please refer to the guidelines.
Reporting Currency
PQR Product Categories | Value of products received during reporting period | Value of products entered by the PR and verified as correct by the LFA in the PQR during reporting period | Variance | Reason for Variance | Cumulative value of products received since Jan 2011 | Cumulative value of products verified as correct by the LFA in the PQR since Jan 2011 | Variance | Reason for Variance
1. Anti-malaria medicines
2. Bed nets
3. Rapid Diagnostic Tests
4. Condoms
5. Anti-retrovirals
6. Anti-TB Medicines
Total | 0 | 0 | 0 |  | 0 | 0 | 0
2. Based on best information available to the LFA, are there any risks of drug stockout at the central level in the next period of implementation? (If yes, please explain in comments box) ! This section should be completed by the LFA based on best information on stock levels at the central level available to the LFA and should not require dedicated visits for on-site checks of stocks. | No | Select
3. PR comments on issues related to the procurement and supply management of pharmaceuticals and health products |  |  |  | LFA analysis on issues related to the procurement and supply management of pharmaceuticals and health products
LLINs are arriving on May 16 2011, expected to be distributed to townships by end of May.

## LFA_Findings&Recommendations
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: | MYN-S10-G07-M
Progress Update - Reporting Period: | Cycle: | Quarter | Number: | 1
Progress Update - Period Covered: | Beginning Date: | 2011-01-01 | End Date: | 2011-03-31
Progress Update - Number: | 1
LFA-specific section: LFA Findings & Recommendations
! Based on the information provided in the previous sections and your understanding of the grant, please summarise any important management issues, proposing a recommendation for each. NB: an issue is considered as 'important' if it impacts or is likely to impact program implementation and results. ! Instead of repeating detailed descriptions of issues covered in other sections, it is acceptable to state the issue and reference the section containing the details.
Functional Areas | Description of Identified Issues (in order of importance) |  |  | LFA Recommendations (in order of importance) | FPM Comments (to be completed upon receipt of the LFA-verified form)
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
Select
LFA_Findings & Recommendations
Select
Yes
No
Select
Program management (including SR management)
Financial management and systems
Monitoring and evaluation
Pharmaceutical & health product management
Other management issues, including: PR capacity to develop quality programmatic and financial reports

## LFA_Cash Reconciliation_5A
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: |  | MYN-S10-G07-M
Disbursement Request - Disbursement Period: |  | Cycle: | Quarter | Number: | 2
Disbursement Request - Period Covered: |  | Beginning Date: | 2011-04-01 | End Date: | 2011-06-30
Disbursement Request - Number: |  | 2
Section 5: LFA-verified Cash Reconciliation & Disbursement Recommendation
A. LFA-VERIFIED CASH RECONCILIATION FOR PERIOD COVERED BY PROGRESS UPDATE
|  |  |  | PR-reported amounts | LFA-verified amounts | LFA Comments on verified amounts (if they are different from those reported by the PR) and PR's explanation of reconciliation adjustments (line 9)
1. Cash Balance: Beginning of period covered by Progress Update (line 10 from Cash Reconciliation section of the period covered by the previous Progress Update): |  |  |  | 0
Add: |  |  |  | 7642241
2. Cash received by the PR from the Global Fund during the period covered by this progress update: (1)
| 3. Cash disbursed to third parties by the Global Fund on behalf of the PR during the period covered by this progress update: (1) |  |  | 0
| 4. Interest received on bank account |  |  | 0
| 5. Revenue from income-generating activities (if applicable) |  |  | 0
| 6. Other income, if applicable (e.g. income from disposal of fixed assets, tax refunds) |  |  | 0
Less: | 7. Total PR cash outflow during period covered by Progress Update (value entered in Section 3A "Total cash outflow"): |  |  | 185234.85
| 8. Net exchange rate gains/losses (gains should be shown with a minus sign; losses should be shown with a plus sign) |  |  | 0
| 9. Reconciliation adjustments (gains should be shown with a minus sign; losses should be shown with a plus sign) |  |  | 0
10. Cash Balance: End of period covered by Progress Update: |  |  |  | 7457006.15 | 0

## LFA_Disbursement Recommend_5B
LFA On-going Progress Review and Disbursement Recommendation
DISBURSEMENT REQUEST PERIOD
Grant number: |  | MYN-S10-G07-M
Disbursement Request - Disbursement Period: |  | Cycle: | Quarter | Number: | 2
Disbursement Request - Period Covered: |  | Beginning Date: | 2011-04-01 | End Date: | 2011-06-30
Disbursement Request - Number: |  | 2
Currency: |  | USD
Section 5: LFA-verified Cash Reconciliation & Disbursement Recommendation
B. LFA-RECOMMENDED DISBURSEMENT AMOUNT AND EXPLANATIONS
Total forecasted net cash expenditures by the Principal Recipient for the period immediately following the period covered
by the Progress Update:
1. Period beginning date: |  | 2011-04-01 | end date: | 2011-06-30 |  | Approved budget amount (reported by PR): |  | 845047 | Forecasted amount (reported by PR): | 845047
[6 empty] | LFA-verified approved budget amount: |  |  | LFA-adjusted forecasted amount:
2a. Cash buffer period (by default)
(cash "buffer") beginning date: |  | 2011-07-01 | end date: | 2011-09-30 |  | Approved budget amount (reported by PR): |  | 925144 | Forecasted amount (reported by PR): | 925144
PR Total Forecast
[6 empty] | LFA-verified approved budget amount: |  |  | LFA-adjusted forecasted amount: |  | 1770191
2b. Additional "buffer" (discretionary, select only if there is a prior agreement with the FPM) (1) | [10 empty] | LFA Total Forecast
0
(cash "buffer") beginning date |  | 2011-10-01 | end date: |  |  | approved budget amount: |  | 0 | forecasted amount: | 0
[6 empty] | LFA-verified approved budget amount: |  |  | LFA-adjusted forecasted amount:
(1) Upon agreement with the FPM, additional Cash buffer can be requested if the PU/DR report contains a completed EFR report or a completed Annex on SR financials, requested by the Secretariat, or if there are any additional GF-specific requirements that cannot be delivered within 45 days. However such requests may or may not be satisfied based on the review of the current PUDR
(2) When the additional (cash "buffer" ) period is 1 or 2months, the approved budget and forecasted amounts should be calculated as prorated values for the period following the regular buffer period.
PR's explanation of any significant variance between forecasted amounts and amounts as originally budgeted.
LFA's explanation of any significant variance between forecasted amounts and amounts as originally budgeted. Please explain any significant variance (based on your judgment) between the forecasted amounts and the amounts as per approved budgets. Please specify the main factors and related amounts that are the major drivers of the variance. NB. Consider the following items when providing the analysis. - Expected timing of payments for any significant budgetary items, - Impact of existing cash balance at SR levels - Current confirmed commitments to be paid during disbursement request period - Current/expected unit prices compared to those in the budget - Change in quantities compared to budget - Exchange rates and inflation - Linkage between budget absorption and programmatic performance to-date. ! The forecast should include any existing commitments (eligible under this grant) as of the end of the reporting period and which are likely to be paid during the disbursement period
Less: | 3. Cash Balance: End of period covered by Progress Update (number 10 from LFA or PR Cash Reconciliation sheet): |  |  |  | PR-reported amounts | LFA-verified amounts | LFA Comments
[5 empty] | 7457006.15 | 0
| 4. Cash "in transit" disbursed to the PR: |  |  |  | 0
| 5. Cash "in transit" disbursed to third parties by the Global Fund on behalf of the PR : |  |  |  | 0
[5 empty] | PR-requested amount | LFA-recommended amount
6. Disbursement Request to the Global Fund for the period immediately following the period covered by the Progress Update, plus additional period (cash buffer): |  |  |  |  | 0 | 0
7. Does the PR's Disbursement Request include funds for health product procurement? |  |  |  |  | Select
8. Exchange Rate (used to translate local currency into grant currency)
|  | Rates used by the PR | LFA-verified rates |  | Name of local currency and LFA comments on the exchange rates used by the PR
| - used to convert Opening Cash Balance | Yes
| - used to convert Closing Cash Balance | No
| - used to convert Total PR Cash Outflow for the Progress Update Period | Yes

## LFA_Overall Performance_6
LFA On-going Progress Review and Disbursement Recommendation
PROGRESS UPDATE PERIOD
Grant number: |  | MYN-S10-G07-M
Progress Update - Reporting Period: |  | Cycle: | Quarter | Number: | 1
Progress Update - Period Covered: |  | Beginning Date: | 2011-01-01 | End Date: | 2011-03-31
Progress Update - Number: |  | 1
Section 6: LFA EVALUATION AND COMMENTS ON OVERALL PERFORMANCE
A. Overall Evaluation and Rating of Grant Performance (including a summary of how financial performance is linked to programmatic achievements)
! The evaluation should be undertaken by taking into account programmatic achievements, financial performance and program issues in various functional areas (M&E, Finance, Procurement, and Program Management, including management of sub-recipients). See Guidelines for more detailed guidance on the completion of this section. ! For RCC grants, this section should cover the period from the RCC start date through the end date of the current Progress Update period. ! For guidance on the methodology for rating overall performance, refer to Annex 2 of Guidelines.
Indicator rating | Select |  | Any major management issues resulting in downgrade? | Select |  | Overall Grant Rating | Select
B. LFA comments on PR planned changes in the program, if any
C. LFA Comments on External Factors Beyond Control of the Principal Recipients that have impacted or may impact program

## LFA_DisbursementRecommendation7
LFA On-going Progress Review and Disbursement Recommendation
LFA Organization / Responsible office:
GENERAL GRANT INFORMATION
Country: |  |  | Union of Myanmar
Disease: |  |  | Malaria
Grant Number: |  |  | MYN-S10-G07-M
Principal Recipient: |  |  | UNOPS
Program Start Date: |  |  | 2011-01-01
Currency: |  |  | USD
PROGRESS UPDATE PERIOD | [7 empty] | DISBURSEMENT REQUEST PERIOD
Progress Update - Reporting Period: |  |  | Cycle: | Quarter | Number: | 1 |  | Disbursement Request - Disbursement Period: |  | Cycle: | Quarter | Number: | 2
Progress Update - Period Covered: |  |  | Beginning Date: | 2011-01-01 | End Date: | 2011-03-31 |  | Disbursement Request - Period Covered: |  | Beginning Date: | 2011-04-01 | End Date: | 2011-06-30
Progress Update - Number: |  |  | 1 |  |  |  |  | Disbursement Request - Number: |  | 2
Section 7: Disbursement Recommendation
A. DISBURSEMENT RECOMMENDATION
| Overall Rating | Select
Indicative disbursement ranges by performance rating (included as a reference)
Performance rating |  |  | Range for cumulative disbursement amount (after the currently recommended disbursement)
A1 | Exceeding expectations |  | Above 95% of cumulative budget through the next reporting period
A2 | Meeting expectations |  | Between 85-105% of cumulative budget through the next reporting period
B1 | Adequate |  | Between 55-95% of cumulative budget through the next reporting period
B2 | Inadequate but potential demonstrated |  | Between 25-65% of cumulative budget through the next reporting period
C | Unacceptable |  | Below 35% of cumulative budget through the next reporting period
1. Cash amount requested by the Principal Recipient from the Global Fund for next disbursement period plus one additional quarter (amount in: USD): | [6 empty] | 0
2. LFA disbursement recommendation (amount in: USD): | [6 empty] | 0
State the amount in words
Cumulative budget through the next period of implementation (including the buffer) |  |  | Cumulative disbursed amount to date (*) |  | Cumulative disbursed after recommended disbursement (including the buffer) |  | % range |  | Is the recommended disbursement within the range?
| 7276967.52 |  |  |  | 0 |  | 0% |  | Select
(*)This data can be obtained from the "Disbursements in detail report (PDF)" (http://www.theglobalfund.org/documents/disbursementdetails.pdf)
3. Rationale for the LFA's disbursement recommendation (if resulting in cumulative disbursement outside the indicative ranges):
B. VERIFICATIONS
The following information provided by the Principal Recipient in its On-going Progress Review and Disbursement Request has been verified: | [8 empty] | Comments regarding verifications, if any:
| Select | Signature on behalf of Principal Recipient is authentic and the person to whom it belongs is authorized to sign the disbursement request
| Select | Conditions Precedent for disbursement and/or Special Conditions, if any, have been met (see Section 2, if applicable).
| Select | Program Expenditures and cash reconciliation have been verified and correspond with the PR's Statement of Sources and Uses of Funds (Cash Flow Statement).
| Select | Programmatic information provided by Principal Recipient in its On-going Progress Review and Disbursement Recommendation has been verified and corresponds with actual program progress.
| Select | Exchange rate stated by Principal Recipient has been verified and is correct.
| Select | PR Bank details verified/corrected by LFA
| Select | Current budget forecasts of the Principal Recipient for the next disbursement period plus buffer period have been reviewed for reasonableness
| Select | LFA has debriefed the Principal Recipient on the key findings (comment on the format of this debriefing)
NB: Please ensure that section 7C Bank Details on the following page is completed if (1) this is a split disbursement (i.e. disbursement going to more than one recipient) or (2) if there have been changes to the bank details since the previous disbursement.
D. Summary of the LFA's approach used for verification of financial, programmatic and procurement data and Quality Assurance undertaken by the LFA
In this section the LFA should indicate, as applicable, what percentage of expenditures was verified at PR level, if any expenditures were verified at SR level, how many site visits were made, what tender documentation was verified, and any other material parts of verification procedures in line with the verification approach agreed upfront between the LFA and GF Secretariat based on country/grant risks. As a good practice, the verification approach needs to be reviewed jointly by the LFA and the Secretariat annually.
NB: The LFA should sign a printed version of the verified PU/DR and send it to the Secretariat as a pdf file by email, or include an electronic signature in the Excel file to be submitted to the Global Fund.
Signed on behalf of the LFA:
Name:
Title:
Date and Place:

## LFA_Bank Details_7C
LFA On-going Progress Review and Disbursement Recommendation
Note for LFAs: This page should be completed by the PR if (1) this is a split disbursement (i.e. disbursement going to more than one recipient) or (2) if there have been changes to the bank details since the previous disbursement. The amounts and bank details below are displayed as entered by the PR. If any of this information is incorrect, please correct them by overwriting with correct information.
7C: LFA-verified Bank Account Details
| Disbursement Request Period | 0
| Summary |  |  |  | Summary
|  | Beneficiary Name | Amount in grant currency |  |  | Beneficiary Name | Amount in grant currency
| Payee 1 - Principal Recipient: |  |  |  | Payee 1 - Principal Recipient:
| Payee 2: |  |  |  | Payee 2:
| Payee 3: |  |  |  | Payee 3:
| Payee 4: |  |  |  | Payee 4:
| Total |  | 0 |  | Total |  | 0
| Payee 1: |  |  |  | Payee 1:
| Beneficiary Name: |  |  | Owner of Bank Account: | Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account: | Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number: | Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address | Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code: | Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other): | Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
|  |  |  | Routing Instructions: |  |  |  | Routing Instructions:
| Payee 2: |  |  |  | Payee 2:
| Beneficiary Name: |  |  | Owner of Bank Account: | Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account: | Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number: | Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address | Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code: | Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other): | Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
|  |  |  | Routing Instructions: |  |  |  | Routing Instructions:
| Payee 3: |  |  |  | Payee 3:
| Beneficiary Name: |  |  | Owner of Bank Account: | Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account: | Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number: | Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address | Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code: | Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other): | Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
|  |  |  | Routing Instructions: |  |  |  | Routing Instructions:
| Payee 4: |  |  |  | Payee 4:
| Beneficiary Name: |  |  | Owner of Bank Account: | Beneficiary Name: |  |  | Owner of Bank Account:
| Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account: | Currency in which beneficiary should receive the funds |  |  | Owner of Bank Account:
| Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number: | Amount in currency in which beneficiary should receive the funds: |  |  | Bank Account Number:
| Amount in Words: |  |  | Bank Address | Amount in Words: |  |  | Bank Address
| Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code: | Exchange rate, date and source (Complete only if currency in which beneficiary should receive the funds is different from the grant currency) |  |  | Bank SWIFT Code:
| Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other): | Equivalent in grant currency (Calculated based on the indicated exchange rate) |  |  | Bank Code (Other):
|  |  |  | Routing Instructions: |  |  |  | Routing Instructions:

## LFA_Annex-SR Financials
LFA On-going Progress Review and Disbursement Recommendation
Annex to PU/DR - LFA-reviewed Sub-recipient financial information ! Completion of this table by the PR and verification by the LFA are discretionary, and should be done upon the Secretariat's request.
Grant number: |  |  |  | MYN-S10-G07-M
Progress Update - Reporting Period: |  |  |  | Cycle: | Quarter |  | Number: | 1
Progress Update - Period Covered: |  |  |  | Beginning Date: | 2011-01-01 |  | End Date: | 2011-03-31
Progress Update - Number: |  |  |  | 1
Currency: |  |  |  | USD
Note for LFAs: The information below is displayed as entered by the PR. If any of this information is incorrect, please correct them by overwriting with correct information.
Name of Entity | Type of Implementing Entity | Date of Most Recent Disbursement to SR | Budget for Reporting Period* | Disbursed during Reporting Period* |  | Cumulative Budget through period of Progress Update* | Cumulative Disbursed through period of Progress Update* | Cumulative Actual Expenditure through period covered by this Progress Update | Cash balance at the end of the period covered by this Progress Update | Variance between Latest Cumulative Expenditure Reported and Cumulative Budget | Expenditure Verified by PR (YES/NO) | PR's explanation of variance (1) between cumulative budget and cumulative expenditure and (2) between cumulative disbursement and cumulative expenditure (mandatory for amounts above $50,000 or equivalent and with more than 10% variance) | LFA Comments on the PR's overall verification efforts of SR expenditure and the explanations of variance provided | Name of Entity | Type of Implementing Entity | Date of Most Recent Disbursement to SR | Budget for Reporting Period* | Disbursed during Reporting Period* | Cumulative Budget through period of Progress Update* | Cumulative Disbursed through period of Progress Update* | Latest Cumulative Actual Expenditure (as per most recent SR reports available at PR level) | End date of period covered in most recent SR report | Variance between Latest Cumulative Expenditure Reported and Cumulative Budget | Expenditure Verified by PR (YES/NO) | PR's explanation of variance (mandatory for amounts above $50,000 and with more than 10% variance)
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
TOTAL |  |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | TOTAL |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
*TOTAL amount for these columns should reconcile with relevant amounts under "1b Disbursed to Sub Recipients" in Section 3A"
** Where the number of SRs is significant (over 10), SRs with small budgets (less than $50,000 or EUR equivalent cumulative each) do not need to be reported separately and the figures can be aggregated in a group called "Other Minor SRs"

## Annex for additional info
Annex 1 | Use these worksheets to provide more detailed information on EFR variances if necessary

## Memo HIV (hidden)
Service Delivery Areas | Impact Indicators | IndicatorTypes | Outcome Indicators | DataSources
Please select… | Please select… | Please select… | Please select… | Please select… |  | Please select…
Prevention: Behavioral Change Communication - Mass media | % of young women and men aged 15-24 who are HIV infected | impact | % of young people aged 15-24 who had sex with more than one partner in the last year | National Health Accounts | Please enter a corresponding indicator here… | Please select disease and Impact/Outcome first
Prevention: Behavioral Change Communication - community outreach | % of adults aged 15-49 who are HIV infected | outcome | % of young people aged 15-19 who have never had sex | DHS/DHS+ (Demographic and Health Survey) | Please enter a data source here…
Prevention: Condom distribution | % of adults and children with HIV still alive 12 months after initiation of antiretroviral therapy (extend to 2, 3, 5 years as program matures) |  | % of young people aged 15-24 who never had sex in the last year of those who ever had sex | MICS (Multiple Indicator Cluster Survey) | Please enter a SDA here…
Prevention: Counseling and Testing | % of infants born to HIV infected mothers who are infected |  | % of young people aged 15-24 reporting the consistent use of a condom with non-regular sexual partners in the last year | AIS (AIDS Indicator Survey)
Prevention: PMTCT | % of most-at-risk population(s) (sex workers, clients of sex workers, men who have sex with men, injecting drug users) who are HIV infected |  | % of young women and men who had sex before the age of 15 | SAMS (Service Availibility Mapping Survey)
Prevention: Post-exposure prophylaxis (PEP) | % of HIV seroprevalence among all newly registered TB patients |  | % of adults and children who are still on treatment after 6 months, 1, 2, 3, 5 years from the initiation of treatment | BSS (Behavioral and Surveillance Survey)
Prevention: STI diagnosis and treatment |  |  | % of injecting drug users who have adopted behaviors that reduce transmission of HIV. | Sentinel surveillance
Prevention: Blood safety and universal precaution |  |  | % of orphaned children compared to non-orphaned children aged 10-14 who are currently attending school | Serological surveys
Treatment: Antiretroviral treatment (ARV) and monitoring |  |  | % of young people aged 15-24 reporting the use of a condom the last time they had sex with a non-regular sexual partner | Prevalence surveys
Treatment: Prophylaxis and treatment for opportunistic infections |  |  | % of people expressing accepting attitudes towards PLWHA, of all people surveyed aged 15-49 | Facility-based survey
Care and support: Care and support for the chronically ill |  |  | % of female sex workers reporting the use of a condom with every client in the last month | Key informant survey
Care and support: Support for orphans and vulnerable children |  |  | % of men who have had sex with a female sex worker in the last year | Specific surveys (to be defined)
TB/HIV collaborative activities: HIV care and support for HIV-positive TB patients | TB/HIV collaborative activities: Intensified case-finding among PLWHA |  | % of men reporting the use of condom the last time they had anal sex with a male partner in the last 6 months | Civil registration systems (vital/disease specific registration)
Supportive environment: Policy development including workplace policy | TB/HIV collaborative activities: Prevention of TB disease in PLWHA |  |  | Census
Supportive environment: Strengthening of civil society and institutional capacity building | TB/HIV collaborative activities: Prevention of HIV in TB patients |  |  | Health service statistics
Supportive environment: Stigma reduction in all settings | TB/HIV collaborative activities: Prevention of opportunistic infections in PLWHA with TB |  |  | Patient register
Supportive environment: Program management and administration |  |  |  | Clinical cohort follow-up studies
HSS: Service delivery | TB/HIV collaborative activities: Provision of antiretroviral treatment for TB patients during TB treatment |  |  | Community services assessment
HSS: Human resources | HSS: PAL (Practical Approach to Lung Health) |  |  | Records: laboratory, patient (e.g. treatment cards), training, certification, other (to be specified)
HSS: Community Systems Strengthening |  |  |  | Operational research
HSS: Information system & Operational research
HSS: Infrastructure
HSS: Procurement and Supply management
HSS: Other, specify

## Memo TB (hidden)
Service Delivery Areas | Impact Indicators | IndicatorTypes | Outcome Indicators | DataSources
please select… | please select… | please select… | please select… | please select…
Improving diagnosis | TB prevalence rate | impact | Case detection | National Health Accounts
Standardized treatment, patient support and patient charter | TB incidence rate | outcome | Treatment success rate | DHS/DHS+ (Demographic and Health Survey)
Procurement and supply management | TB mortality rate |  | Smear conversion rate | MICS (Multiple Indicator Cluster Survey)
M&E |  |  |  | AIS (AIDS Indicator Survey)
TB/HIV |  |  |  | SAMS (Service Availibility Mapping Survey)
MDR-TB |  |  |  | BSS (Behavioral and Surveillance Survey)
High-risk groups |  |  |  | Sentinel surveillance
HSS (beyond TB) |  |  |  | Serological surveys
PAL (Practical Approach to Lung Health) |  |  |  | Prevalence surveys
PPM / ISTC (Public-Public, Public-Private Mix (PPM) approaches and International standards for TB care) |  |  |  | Facility-based survey
ACSM (Advocacy, communication and social mobilization) |  |  |  | Key informant survey
Community TB care |  |  |  | Specific surveys (to be defined)
Programme-based operational research
Other:Specify
Supportive environment: Program management and administration |  |  |  | Civil registration systems (vital/disease specific registration)
Census
Health service statistics
Patient register
Clinical cohort follow-up studies
Community services assessment
Records: laboratory, patient (e.g. treatment cards), training, certification, other (to be specified)
Operational research
R&R TB system, quarterly report
R&R TB system, yearly management report
Other Surveillance reports, specify

## Memo Malaria (hidden)
Service Delivery Areas | Impact Indicators | IndicatorTypes | Outcome Indicators | DataSources
please select… | please select… | please select… | please select… | please select…
Prevention: Behavioral Change Communication - Mass media | Death rates associated with Malaria: all-cause under-5 mortality rate in highly endemic areas | impact | % of U5 children (and other target groups) with malaria/fever receiving appropriate treatment within 24 hours (community/health facility) | National Health Accounts
Prevention: Behavioral Change Communication - community outreach | Incidence of clinical malaria cases (estimated and/or reported) | outcome | % of U5 children (and other target group) with uncomplicated malaria correctly managed at health facilities | DHS/DHS+ (Demographic and Health Survey)
Prevention: Insecticide-treated nets (ITNs) | Anaemia prevalence in children under 5 years of age |  | % of U5 children (and other target groups) admitted with severe malaria and correctly managed at health facilities | MICS (Multiple Indicator Cluster Survey)
Prevention: Malaria prevention during pregnancy | Prevalence of malaria parasite infection |  | % of children U5 sleeping under an ITN the previous night | MIS (Malaria Indicator Survey)
Prevention: Vector control (other than ITNs) | Laboratory-confirmed malaria cases seen in heath facilities |  | % of households with at least one ITN | SAMS (Service Availibility Mapping Survey)
Prevention: other - specify | Laboratory-confirmed malaria deaths seen in health facilities |  | % of pregnant women (and other target groups) sleeping under an ITN the previous night | BSS (Behavioral and Surveillance Survey)
Treatment: Prompt, effective anti-malarial treatment | Malaria-attributed deaths in sentinel demographic surveillance sites |  | % of pregnant women on Intermittent preventive treatment (IPT) according to national policy (specific to Sub-Saharian Africa) | Sentinel surveillance
Treatment: Home based management of malaria | API (Annual Parasite Index) (specific to Latin America and Asia) |  | % of households in malaria areas protected by IRS | MOH (routine HIS or HMIS)
Treatment: Diagnosis |  |  |  | RBM (Roll Back Malaria)
Treatment: other - specify |  |  |  | Serological surveys
Supportive environment: Monitoring drug resistance |  |  |  | Prevalence surveys
Supportive environment: Monitoring insecticide resistance |  |  |  | Facility-based survey
Supportive environment: Coordination and partnership development (national, community, public-private) |  |  |  | Key informant survey
Supportive environment: other - specify |  |  |  | Specific surveys (to be defined)
Supportive environment: Program management and administration |  |  |  | Civil registration systems (vital/disease specific registration)
HSS: Service delivery |  |  |  | Census
HSS: Human resources |  |  |  | Health service statistics
HSS: Community Systems Strengthening |  |  |  | Patient register
HSS: Information system & Operational research |  |  |  | Clinical cohort follow-up studies
HSS: Infrastructure |  |  |  | Community services assessment
HSS: Procurement and Supply management |  |  |  | Records: laboratory, patient (e.g. treatment cards), training, certification, other (to be specified)
HSS: other - specify |  |  |  | Operational research
Questionnaire

## Definitions-lists-EFR (hidden)
Please Select…
Prevention
Treatment
Care and Support
TB/HIV Collaborative Activities
Supportive Environment
Health System Strengthening (HSS)
Please Select…
Prevention
Treatment
Supportive Environment
Health System Strengthening (HSS)
Please Select…
Prevention: Behavioral Change Communication - Mass Media
Prevention: Behavioral Change Communication - Community Outreach
Prevention: Insecticite-treated nets (ITNs)
Prevention: Malaria in pregnancy
Prevention: Vector control (other than ITNs)
Prevention: Other - specify
Treatment: Prompt, effective antimalatial treatment
Please Select…
TB Detection
TB Treatment
TB/HIV Collaborative Activities
Supportive Environment
Health System Strengthening
Please Select…
Improving diagnosis
Standardized treatment, pation support and patient charter
Procurement and Supply management
M&E
TB/HIV
MDR-TB
High-risk groups
Please Select…
FBO
NGO/CBO/Academic
Private Sector
Ministry Health (MoH)
Other Government
UNDP
Other Multilateral Organization